Supplementary financial information for the Advisory Committee on Administrative and Budgetary Questions*

Proposed programme budget for the biennium 
2012-2013

Part XIII

Development Account

Section 36

Development Account

Section 36

Development Account

List of projects proposed to be funded from the Development Account during the biennium 2012-2013

| Project title |  | Amount (United States dollars) |  |  |  |
| --- | --- | --- | --- | --- | --- |
| A. Capacity building for removing constraints in utilising trade-related international support measures for Least Developed Countries (DESA) |  |  |  | 670,000 |  |
| B. Strengthening capacities of the public sector in Least Developed Countries to deliver quality services equitably through the transfer and adaptation of innovative practices (DESA) . . . . . . . . . . . . . . . . . . |  |  |  | 640,300 |  |
| C. Strengthening national capacities of conflict-affected countries to manage water scarcity and droughts (DESA) |  |  |  | 570,000 |  |
| D. Supporting the development of low carbon technologies for resilient green economies in small island developing States (DESA). . . . . . . . . . |  |  |  | 650,000 |  |
| E. Climate change financing for forests: Reducing Emissions from Deforestation and forest Degradation - Plus (REDD+) and its impacts on financing for other functions of forests worldwide (DESA) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 600,000 |  |
| F. Fostering Private-Public Partnerships to strengthen national capacities for designing, implementing and evaluating development-oriented macroeconomic policies to generate employment, growth and poverty reduction (DESA) |  |  |  | 400,000 |  |
| G. Helping developing countries measure progress towards achieving a Green Economy (DESA) |  |  |  | 800,000 |  |
| H. Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level (DESA). . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 400,000 |  |
| I. Supporting small islands developing States in their efforts to build economic resilience (UNCTAD). . . . . . . |  |  |  | 397,000 |  |
| J. Accelerating progress of selected West-African countries towards the achievement of Internationally Agreed Development Goals, particularly MDG 8, through trade-related training and capacity building (UNCTAD) |  |  |  | 577,000 |  |
| K. Capacity building for the formulation and implementation of MDG-oriented trade policies in developing countries contributing to accelerating achievement of Millennium Development Goals in the context of multiple and interrelated development challenges (UNCTAD) |  |  |  | 694,000 |  |
| L. Addressing the impact of trade and trade agreements on employment in developing countries (UNCTAD) . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 232,000 |  |
| M. Strengthening of capacities of trade and planning ministries of selected Least Developed Countries on developing and implementing trade strategies that are conducive for poverty reduction . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 641,000 |  |
| N. Building national capacities for promoting Foreign Direct Investment in Green and other growth sectors (UNCTAD) . . . . . . . . . . |  |  |  | 461,000 |  |
| O. Promoting sustainable business models for development: Investing in the poor, for the poor and with the poor (UNCTAD) |  |  |  | 462,000 |  |
| P. Strengthening pro-growth macroeconomic management capacities for enhanced regional financial and monetary cooperation among selected countries of Latin America and the Caribbean, and West and Central Africa (UNCTAD) |  |  |  | 555,000 |  |
| Q. Mainstreaming ecosystem service into country’s sectoral and macroeconomic policies and programmes (UNEP) . . . . . . . . . . . . . . |  |  |  | 542,000 |  |
| R. Integrating environmental sustainability in the United Nations Development Assistance Framework and United Nations common country programming processes (UNEP) . . . . . . …............................. |  |  |  | 541,000 |  |
| S. Development of a review system for the effective national implementation of Multi-lateral Environmental Agreements (UNEP) |  |  |  | 543,000 |  |
| T. Strengthening the capacities of the International Conference on the Great Lakes Region member states to address the land and property issues of Internally Displaced Persons and refugees, with a specific emphasis on women's land and property rights (UN-Habitat) |  |  |  | 452,000 |  |
| U. Strengthening capacity of policy makers in South East Asia for promoting policies and developing plans for improved wastewater treatment and reuse in urban and peri-urban areas (UN-Habitat) |  |  |  | 348,000 |  |
| V. Integrating crime, corruption, drugs, and terrorism related issues into the preparation of national development plans and processes (UNODC). . . . . . . . . . . |  |  |  | 650,000 |  |
| W. Strengthening the capacity of Civil Registration and Vital Statistics systems in Africa to produce continuous and reliable indicators for measuring progress on the development agenda (ECA). ... . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 682,000 |  |
| X. Strengthening capacity of African countries to promote the use of renewable energy to achieve sustainable development and poverty reduction (ECA) |  |  |  | 703,000 |  |
| Y. Capacity building for risk and disaster management systems, through use of Information and Communications Technology in Africa (ECA)….. |  |  |  | 689,000 |  |
| Z. Strengthening capacities for the development of regional agricultural value chains in Africa (ECA). . . . . . . . . . . . . . . |  |  |  | 499,000 |  |
| AA. Strengthening the capacities of developing countries and countries with economies in transition to facilitate legitimate border crossing, regional cooperation and integration (ECE). . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 750,000 |  |
| AB. Promoting energy efficiency investments for climate change mitigation and sustainable development (ECE). . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 1,250,000 |  |
| AC. Towards productivity convergence: Trade, financing and technology for small scale enterprise (ECLAC) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 575,000 |  |
| AD. Towards a low-carbon economy: Policy options for energy efficiency and innovation (ECLAC) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 478,000 |  |
| AE. Time for equality: Strengthening the institutional framework of social policies (ECLAC) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 661,000 |  |
| AF. Strengthening the capacities of Latin America and Asia to develop and improve labour training systems and to protect workers against unemployment (ECLAC). |  |  |  | 754,500 |  |
| AG. Strengthening Information and Communications Technology capacities for disaster risk reduction and development: Addressing information, knowledge and policy gaps in Asia (ESCAP) . . . . . . . . . |  |  |  | 600,600 |  |
| AH. Strengthening capacities in countries with special needs on designing and implementing economic and social development policies to accelerate progress towards achieving the Millennium Development Goals (ESCAP). . . . . . . . . . . . . |  |  |  | 643,500 |  |
| AI. Interregional cooperation to strengthen national capacities to measure progress in achieving gender equality and women's empowerment (ESCAP) . . . . . . . . . . . . . |  |  |  | 686,400 |  |
| AJ. Deepening regional connectivity: Strengthening capacities of Asian developing countries to increase intra-regional trade by implementing paperless trade and transport facilitation systems (ESCAP) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 854,000 |  |
| AK. Institutional and capacity building project for Arab Parliaments and other stakeholders for the implementation of Security Council resolution 1325 (2000) on Women, Peace and Security (ESCWA) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 510,000 |  |
| AL. Academy of ICT Essentials for Government Leaders in the ESCWA Region (ESCWA) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 509,000 |  |
| AM. Developing the capacities of the Arab Countries for climate change adaptation by applying integrated water resource management tools (ESCWA) . . . . . . . . . . . |  |  |  | 517,000 |  |
| AN. Strengthening capacities to utilise workers’ remittances in financing for development (ESCWA) . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . . |  |  |  | 464,000 |  |
|  | Total |  | 23,651,300 |  |  |

- This supplementary information contains indicative resource requirements of the projects to be financed under the Eight tranche of the Development Account and should be read in conjunction with the fascicle for the Development Account (A/66/6 (Sect 36)), which contains the background, objective of the Organization, relationship to the biennial programme plan and priorities for the period 2012-2013 and the Millennium Declaration Goals (MDG), and expected accomplishments and indicators of achievement.

- The type of activities and the amounts by budget line are of an indicative nature. The implementing entities will, based on further consultations with stakeholders (implementing partners and target groups), prepare detailed project documents with a thorough analysis of issues and needs involved and provide a detailed implementation plan. All the project documents will be reviewed by the Programme Manager of the Development Account, the Department of Economic and Social Affairs, prior to resources being released.

| A. Capacity building for removing constraints in utilizing trade-related international support measures for Least Developed Countries |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with the ESCAP, ECA, the International Trade Centre, UNCTD, the World Trade Organization, and the Office of the High Representative for the Least Developed Countries, Landlocked Developing Countries and small island developing States |  | Duration: 2012 – 2015 |  |
| Objective: To increase national capacity in LDC governments to access and effectively use the trade-related international support measures for advancing LDC development strategies in addressing structural handicaps and economic vulnerability. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 242.0 Travel 112.0 Contractual services 78.0 Operating Expenses 2.4 Equipment 19.2 Workshops/training 186.4 Total 670.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance A total of $30,000 is required for general temporary assistance in support of project implementation ($6,000 x 5 months) Consultants International Consultants ($122,000): A total of $52,000 is required for two international consultants for providing guidance and reviewing country specific diagnostic studies (a), for participating as resource persons in the workshops foreseen under activities (b) and (d) and deliver training activities under (c). A total requirement comprises (2 work-months x $8,000 x 2 consultants = $32,000) plus (travel to 2 workshops each x $5,000 x 2 consultants = $20,000); (ii) A total of $56,000 is required for international consultants for the design, implementation and undertaking training activities related to the economy-wide (CGE) model under activities (f) and (g) for a total of (4 work months x $8,000 = $32,000) plus (travel to the four project countries x $6,000 = $24,000); and (iii) One international consultant to conduct an external evaluation for 1 work-month plus travel = $14,000 National Consultants ($120,000): A total of $120,000 is required for four national consultants to lead the national country teams in undertaking activity (a) and to act as the coordinator within the country and to liaise with the three other country teams (for the purpose of learning from each others project implementation): (1.5 work-months x $5000 x 4 consultants = $30,000); (travel to 2 workshops in support of (b) and (d): (4 consultants x 2 workshops x $2,500 = $20,000); (training activities in support of activity (c): (1.5 work-months x $5000 x 4 consultants = $30,000); (national consultants in support of activity (d) for the duration of 1 work-month (1 work-month x $5000 x 4 consultants = $20,000); and national consultants are required in the data collection and training in the use of the economy-wide model under activity (f) and (g) for a total of (1 work month each x 5,000 = $20,000) Travel DESA staff: In support of backstopping the capacity building activities under (a) and (c): (one staff travelling to four project countries amounting to 8 missions x $7,000 = $56,000. Also, (travel to two workshops under activities (b) and (e) of two staff members x $7,000 ) = $28,000; Other international staff: Participation of other UN System staff as resource persons in support to activities (b) and (e): ($7,000 per person x 2 persons x 2 workshops) = $28,000 Contractual services Translation of documents in support of activities (a) through (g) = $15,000; Contracts with local institutions in the four project countries in support of the implementation of activities (d) and (e): ($8,000 per institute x 4 countries) = $32,000; A total of $31,000 is required for the design, implementation and training activities related to the web-based information portal under activity (f) Operating expenses: In support of activities (b) and (e) Equipment In support of all activities purchase one PC and software licensing per project country ($4,800 x 4 country teams) = $19,200 Workshops Two workshops in support of activities (b) and (e): (2 x $3,800 per participant x 6 participants x 4 project countries) = $182,400; Conference facilities and services for 2 workshops = $4,000 |  | 30 000 242 000 112 000 78 000 2 400 19 200 186 400 |

| B. Strengthening capacities of the public sector in Least Developed Countries to deliver quality services equitably through the transfer and adaptation of innovative practices |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with UNODC, the United Nations Development Fund for Women, United Nations Human Settlements Programme |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen capacities of the public sector in least developed countries to deliver equitable public services, including basic services. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 120.0 Expert group meetings 28.0 Travel 60.0 Contractual services 50.0 Operating expenses 3.8 Workshops 378.5 Total 640.3 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International consultants ($60,000): Three international consultants to prepare background papers and serve as resource persons respectively in the capacity building workshops (b) and in the workshops for 2 work months (d): ($10,000 plus $5,000 for travel costs, per consultant x 3 = $45,000); (One international consultant external evaluation for 1 work-month plus travel = $15,000) Regional consultants ($60,000): Three regional consultants to prepare training modules for workshops and three consultants to adapt the Manual for the transfer of innovation already developed by DESA and UN-HABITAT to local conditions in support of the adaptation of a good practice and assist in the design of the transfer implementation plan in support of (d) for 2 work months: ($6,000 plus $4,000 each for travel costs to attend the transfer workshops x 6 = $60,000) Expert Group Meeting One expert group meeting (7 experts x $4,000 = $28,000) to define the criteria and methodology for both selecting the good practices to be adapted, as well as the countries that will adapt the good practices Travel DESA staff; Travel of staff to organize and facilitate 1 expert group meeting $10,000, 1 capacity building workshop $10,000, 3 knowledge-transfer workshops, including study tours for $30,000 and 2 advisory services for $10,000 = $60,000 Contractual services Designing on-line training courses ($25,000): Contractual services will be needed for designing online training courses ($12,500 x 2), which will be hosted and run by the United Nations Public Administration Network Management Unit Publication ($15,000): The materials prepared by consultants and staff as well as emanating from the expert group meeting and capacity building workshops will be synthesized into a publication to sustain learning (Editing = $6,000, lay-out and graphics = $5,000, and printing = $4,000) Interpretation ($10,000): Interpretation English/French will be required for one capacity-building workshop ($570 per day x 3 interpreters for a total of $8,550 plus equipment = $1,450) Operating expenses: In support of activities (a), (b), and (d) Workshops Capacity building workshop: A total of $171,500 for two capacity building workshops in support of (b) for a total of 49 participants representing respectively Francophone and Anglophone least developed countries at $3,500 per participant. These workshops will give an opportunity to a wide range of countries in Africa to increase their awareness of the available innovations Practitioner-to-practitioner knowledge transfer workshops: A total of $207,000 for three workshops in support of activity (d): (each activity will have a maximum of 10 participants from least developed countries) for public sector managers for one week ($6,900 x 10 participants x 3). The workshops will be held in the innovator’s country. |  | 120 000 28,000 60 000 50 000 3 800 378 500 |

| C. Strengthening national capacities of conflict-affected countries to manage water scarcity and droughts |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with ESCWA, ECA, UNEP, DPKO, FAO, and the United Nations International Strategy for Disaster Reduction |  | Duration: 2012 – 2015 |  |
| Objective: To enhance the effectiveness of ex-ante drought planning, monitoring and implementation of conflict-sensitive drought-management plans and coping strategy capacities in water scarce countries affected by conflict. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 30.0 Consultants 130.0 Expert group meetings 40.0 Travel 91.0 Contractual services 68.0 Operating expenses 1.0 Workshops 210.0 Total 570.0 | ## Detailed budget (US dollars) |  |  |
|  | General temporary assistance A provision of $30,000 is required to cover general temporary assistance is support of project implementation ($6,000 x 5 months) Consultants International Consultants ($72,000): Provision of $72,000 is required to cover specialized expertise and therefore fees and travel expenses of consultants related to capacity building and further development and piloting methodologies included in toolkit. Provision includes: In support of (a):specialized expertise for conducting a study and develop an analytical report that maps out existing knowledge and practices and identify critical gaps in the area of ex-ante drought management in conflict-affected countries ($14,000); In support of (b): participation in expert advisory group meeting to discuss the findings of the analytical report, gather further information and assess experiences and status of methodologies for conflict-sensitive ex-ante drought management in conflict-affected countries ($6,000); In support of (c): specialized expertise for producing guidance notes package on conflict-sensitive ex-ante water scarcity and drought management for national planners, policy makers and stake-holders in conflict-affected countries ($40,000); One international consultant external evaluation for 1 work-month plus travel ($12,000) National Consultants ($58,000): Provision of $58,000 is required to cover specialized expertise and therefore fees and travel expenses of consultants related to capacity building and further development and piloting methodologies included in toolkit. Provision includes: In support of (e): local/regional expertise in conducting pilot country-specific studies on ex-ante water scarcity and drought management ($22,000); In support of (g): 3 train of trainers national workshops (one in each participating country) for fees and travel costs ($13,000); In support of (h): 3 national interventions (one in each participating country) for fees and travel costs ($13,000); In support of (i): 2 regional workshops (one in East Africa/North Africa and one in West Asia) for fees and travel costs ($10,000) Expert group meeting In support of (b), provision of $40,000 is required in support of convening an expert advisory group meeting. Total number of participants expected to be 20 of which only 10 experts will be sponsored by this project Travel DESA staff: Provision of $91,000 is required for missions for international staff to prepare national assessments and implement workshops regionally and in participating countries. Provision includes: In support of (b): organizing and attending the expert advisory group meeting for 2 staff ($12,000); In support of (e): 3 assessment missions (one to each participating country) for 1 staff ($19,000); ii) In support of (g): 3 national workshops (one in each participating country) for 1 DESA staff ($19,000 plus 1 regional staff $10,000 = $29,000); In support of (h): 3 national interventions (one in each participating country) for 1 staff ($19,000); In support of (i): 2 regional workshops (one in East Africa/North Africa and one in West Asia) for 1 staff ($12,000) Contractual services A provision of $68,000 is required in support of the following contractual services (One contract for design a training framework and produce training modules based on the guidance notes package, in support of (d): $20,000); Three contracts to produce training materials specific to each pilot country, in support of activity (g): (3 x $10,000 = $30,000); Translation of English documents into Arabic in support of all activities ($18,000) Operating expenses: In support of activities (g), (h), and (i) Seminars and Workshops A provision of $210,000 is required for organizing 8 regional workshops and national interventions: In support of (g): 3 national workshops (one in each participating country) for (15 national participants residing outside the capital $50,000 plus costs for conference facilities $3,000 for a total of $53,000); In support of (i): 2 regional workshops (one in East Africa/North Africa and one in West Asia) for (20 participants $100,000 plus for costs for conference facilities $4,000 for a total of $104,000); and In support of (h): 3 national interventions (one in each participating country) such as working group meetings, stakeholder consultations or other strategically targeted activities for (15 national participants residing outside the capital $50,000 plus costs for conference facilities $3,000 for a total of $53,000) |  | 30 000 130 000 40 000 91 000 68 000 1 000 210 000 |

| D. Supporting the development of low carbon technologies for resilient green economies in small island developing States (SIDS) |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with UNEP and ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: To enhance the capacities of small island developing States to transform energy use to low carbon intensity while accommodating increasing demands for fresh water production and energy to support resilient green economies. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 30.0 Consultants 168.2 Expert group meetings 54.6 Travel 149.6 Contractual services 61.2 Operating expenses 5.0 Study tours 40.0 Workshops 141.4 Total 650.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance A provision of $30,000 is proposed to cover general temporary assistance in support of regional project implementation ($6,000 x 5 months) Consultants International consultants ($95,000): To carry out independent engineering studies in support of activities (f) and (g): baselines and feasibility studies to attract investment finance, including one international consultant to conduct an external evaluation (10 work-months x $9,500) = $95,000 National consultants ($73,200): National/regional consultants in support of activities (f) and (g): for local surveys, measurements and analysis (12 work-months at $6,100/month) = $73,200 Expert group meetings Travel of seven experts to 1 expert group meeting in support of activity (b): Bangkok ($7,800 x 7 experts = $54,600) from the academic community with energy research background, representatives from SIDS institutions (Secretariat of the Pacific Community, Caribbean Community, Intergovernmental Oceanographic Commission), air compressor manufacturers, pumping and pipeline providers Travel DESA staff ($83,600): Staff travel in support of activities (b), (c) and (d): to 2 national workshops, 2 regional workshops, 4 advisory services (8 missions x $9,200) = $73,600 and 1 expert group meeting in Bangkok $10,000 UNEP staff ($66,000): Organizing and coordinating in support of activities (b), (c) and (d): the expert group meeting, national and regional workshops for two UNEP staff at an average cost of ($6,600 x 5 missions x 2 staff) = $66,000 Contractual services Institutional contracts to perform energy modelling and organization of national and regional workshops in support of activities (c) and (d) Operating expenses: In support of activities (b), (c), and (d) Study tours Visits of local experts and/or decision makers from pilot countries to observe Sea Water Cooling and/or Energy Storage sites in operation and energy storage systems in Africa, USA, and Europe ($5,000 x 8 visits) = $40,000, in support of activity (e) Seminars and Workshops Organize 2 national workshops as well as 2 regional workshops in support of activities (c) and (d): (22 participants x 2 regional workshops x $3,100) = $136,400; Conference costs for 2 national and 2 regional workshops $5,000 |  | 30 000 168 200 54 600 149 600 61 200 5 000 40 000 141 400 |

| E. Climate change financing for forests: Reducing emissions from Deforestation and Forest Degradation –Plus (REDD+) and its impacts on financing for other functions of forests worldwide |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA |  | Duration: 2012 – 2015 |  |
| Objective: To assist decision-makers in developing countries to effectively harness funding from new and emerging sources of forest financing, including REDD+, by addressing gaps in forest financing. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 53.0 Travel 72.0 Contractual services 144.0 Operating expenses 2.0 Workshops 329.0 Total 600.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International Consultants: One international consultant as resource person in two international workshops (b) and (c) for ($10,000 x 2 months plus travel of $10,500 x 2) = $41,000; One international consultant external evaluation for 1 work-month plus travel = $12,000 Travel Travel of staff to two international workshops (b), (c) and (e) plus six advisor services ($9,000 x 8) = $72,000 Contractual services To cover preliminary studies on geographical distribution of REDD+ funding and design communication strategies, in support of activity (e). The amount includes $54,000 for 4 studies on geographic distribution, $54,000 for 4 studies on thematic distribution, and $36,000 for the development of a draft framework of results/outcomes of the 8 studies on geographic/thematic distribution of REDD+. Operating expenses: In support of activities (b) and (c) Workshops Provision to cover the participation of about (60 participants x $2,700 x 2 workshops) = $324,000 for the international workshop on geographical and thematic distribution of REDD+ under activities (b) and (c); Conference costs in support of activities (b) and (c) of $5,000 is included in the estimate |  | 53 000 72 000 144 000 2 000 329 000 |

| F. Fostering Private-Public Partnerships to strengthen national capacities for designing, implementing and evaluating development-oriented macroeconomic policies to generate employment, growth and poverty reduction |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in cooperation with UNDP and UN regional commissions |  | Duration: 2012 – 2015 |  |
| Objective: To foster effective public-private partnerships in developing countries, to design, implement and evaluate development-oriented macroeconomic policies, ensuring broad stakeholder participation and enhancing accountability and transparency in macroeconomic policy-making processes. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 100.4 Travel 91.5 Operating expenses 2.9 Workshops 205.2 Total 400.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International Consultants ($62,000): International consultants to develop the six guidance notes, as envisaged in (d). The consultants will also develop the course curriculum for the training programmes: ($400/day for 100 working days) = $40,000; International consultant to compile the reports of six national workshops and three regional-training programmes and produce a final report on the outcomes of the project ($400/day for 30 working days) = $12,000; One international consultant external evaluation for 1 work-month plus travel = $10,000 National Consultants ($38,400): One national consultant to facilitate each of the national workshops (b). National workshops will coincide with the three regional training programmes. The national consultants will also be responsible for writing the final report and recommendations of each national workshop ($6,400 x 6 consultants) = $38,400 Travel UN staff: The project will avail of UN staff (experts and economists) to provide necessary training in the regional training workshops (c). The UN experts will be invited to the three training programmes ($6,100 x 3 x 2 staff) = $36,600. One DESA staff will attend three training programmes and six national workshops ($6,100 x 9 x 1) = $54,900 Operating expenses: In support of activity (c) Workshops A total of 60 participants from monetary and financial authorizes, chambers of commerce and national media will be invited to take part in the three regional training programmes (c) ($3,200 x 20 x 3) = $192,000; Conference costs in support of (b): ($1,000 x 6) = $6,000 plus (c) ($2,400 x 3- = $7,200 |  | 100 400 91 500 2 900 205 200 |

| G. Helping developing countries measure progress towards achieving a Green Economy |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with ESCWA, ECA, ESCAP, ECLAC, UNCTAD, and UNEP |  | Duration: 2012 – 2015 |  |
| Objective: To improve the capacity of national statistical offices in developing countries to measure progress towards achieving a Green Economy, through utilization of a comprehensive set of economic and environmental indicators. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 286.0 Travel 140.0 Operating expenses 6.0 Workshops 368.0 Total 800.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International consultant: One international consultant to prepare the external evaluation ($16,000) Regional consultants ($270,000): Regional consultant to assess the statistical frameworks in support of activity (a) ($102,000 for fees and travel); act as resource person at 8 regional workshop/seminar in support of activities (b) and (d) ($12,000 for fees and travel x 8) = $96,000; and provision of 16 advisory mission travels to pilot countries in the region activity (c) ($4,500 per consultant mission x 4 countries x 4 regions) = $72,000 Travel DESA staff: Organizing and coordinating the 8 regional workshops/seminars in support of activities (b) and (d) ($7,500 per person x 2 persons x 8 workshops) = $120,000; Regional Commission’s staff/ other UN staff: Participating in 8 regional workshops/seminars in support of activities (b) and (d) ($2,500 per person x 1 person x 8 workshops) = $20,000 Operating expenses: In support of activities (a), (b) and (d) Workshops Regional workshops (two each for four regions): 8 regional workshops/seminars in support of activities (b) and (d). ($3,000 per participant x 14 participants x 2 workshops x 4 regions = $336,000; Conference costs in support of (b) and (d) = $8,000; Interpretation costs in support of (b) and (d) = $24,000. |  | 286 000 140 000 6 000 368 000 |

| H. Strengthening the geospatial information management capacities of developing countries for better policy making at national, regional and international level |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: DESA, in collaboration with ESCWA, ECA, ECE, ECLAC, and the Department of Peacekeeping Operations |  | Duration: 2012 – 2015 |  |
| Objective: To improve accessibility of timely, reliable and policy relevant geospatial data for users, especially policy decision makers and researchers at national, regional and international levels. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 18.0 Consultants 55.0 Expert group meeting 25.0 Travel 76.0 Operating expenses 4.5 Study tours 24.0 Workshops 197.5 Total 400.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance A provision of $18,000 is required to cover general temporary assistance is support of project implementation ($6,000 x 3 months) = $18,000 Consultants International Consultants ($25,000): International consultants for preparing training materials and travel to the expert group meeting, in support of activities (a) and (b) (2 work months x $6,000 per month) = $12,000 + $5,000 for consultant(s) travel) = $17,000; One international consultant to conduct an external evaluation $8,000 National / Regional consultants ($30,000): National/regional consultants to assist with the provision of base material for the guidelines, to act as resource persons at the regional workshops and to develop country database prototypes, in support of activities (a), (c) and (d). ($2,500 x 12 work months) = $30,000 Expert Group Meeting One expert group meetings in support of activity (b) ($2,500 x 10 participants) = $25,000 Travel DESA staff: Organizing and coordinating the 5 regional workshops and one expert group meeting, as well as supporting database prototype development in two pilot countries in support of activities (b), (c), and (d). ($6,000 x 8) = $48,000; Regional Commissions’ staff/ other UN staff: Participating as resource persons in the 5 regional workshops as well as providing support to the 2 pilot countries in support of activities (b), (c), and (d). ($4,000 x 7) = $28,000 Operating Expenses : In support of activities (a), (b), and (c) Study Tours Study tours to strengthen the capacity of the National Statistics Offices/National Mapping Agencies, in support of (e). ($2,400 x 10) = $24,000 Workshops 5 regional workshops, in support of (c). ($2,500 x 15 participants x 5 workshops) = $187,500. Venue and equipment rental in support of (b) and (c) $10,000 |  | 18 000 55 000 25 000 76 000 4 500 24 000 197 500 |

| I. Supporting small island developing States (SIDS) in their efforts to build economic resilience |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To support selected SIDS in the Atlantic Ocean, Caribbean basin, Pacific Ocean and Indian Ocean regions in their efforts to increase resilience to external economic shocks, notably by enhancing their economic specialization. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 36.0 Consultants 124.0 Travel 84.0 Operating Expenses 1.0 Contractual Services 6.0 Workshops 146.0 Total 397.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform research, drafting and editing tasks toward the publication envisaged as activity (d) (three work-months at P-3 or P-4 level x $12,000) = $36,000 Consultants Regional consultants: Regional expertise to carry out field tasks of data collection, analysis and advisory services under the guidance of UNCTAD staff.; ($6,400 x 10 work-months of experts for activities (a), (b) and (c)) = $64,000 National consultants: Local personnel for follow-up tasks with local sources of data: ($5,000 x 8 work-months of experts for activity (a)) = $40,000 Project evaluation: International consultant, 1 month + travel: $20,000 Travel 9 field missions for activities (a), (b) and (c) at approximately $9,333 per mission Operating Expenses: Postage and communication costs: activities (a), (c) and (d) Contractual Services Printing services for the publication: activity (d) Seminars and Workshops One study tour in support of activity (c): ($46,000); Regional seminars/workshops: (1 seminar/workshop in the Caribbean x $20,000) = $20,000; (2 seminars/workshops in the Atlantic/Indian Ocean x $20,000) = $40,000); (2 seminars/workshops in the Pacific x $20,000 in support of activity (c), 10 participants per event) = $40,000 |  | 36 000 124 000 84 000 1 000 6 000 146 000 |

| J. Accelerating progress of selected West-African countries towards the achievement of internationally agreed development goals, particularly MDG 8, through trade-related training and capacity building |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To build sustainable trade-related capacities in the selected West African countries through the increased use of e-learning tools. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 48.0 Consultants 109.0 Travel 59.2 Contractual services 20.0 Operating expenses 18.8 Workshops 322.0 Total 577.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance related to preparation and contribute to the implementation of the project under activities (a,b,c,e) ( $12,000 x 4 months) = $48,000 Consultants International and regional consultants for analysis of existing technical capacity, in support of activities (a), (b), (c) and (d): (8 countries x 1,000 per country + $4,000 x 8 countries for travel = $ 40,000; Training of trainers and training of distance learning tutors (2 times x $ 3,000 + $ 8,000 x 2 for travel) = $22,000; International consultants for content delivery (18 days x $500 per day + $7,000 x 4 for travel) = $37,000 Consultant for external evaluation: $10,000 Travel UNCTAD staff / other UN agencies staff participating as resource persons in expert meetings: ($7,400 x 8 activities/persons) = $59,200, is support of activities (a) and (f) Contractual services Publications (printing in French and English) $10,000; development of training= DVDs and E-learning material (on-line courses) $10,000, in support of activities (c) and (e) Operating expenses In support of activities (a) to (f) Seminars and Workshops 2 x training of training and tutors: (2 x 8 persons at $4,000 /person) = $64,000; Delivery of e-learning seminars: ($5,000 x 4 deliveries) = $20,000; 4 x face-to-face follow up deliveries: (4 x 15 persons at $3,500 /person) = $210,000; Regional meeting for best practice and networking with the Secretariat of ECOWAS ($7,000 x 4 = $28,000 |  | 48 000 109 000 59 200 20 000 18 800 322 000 |

| K. Capacity building for the formulation and implementation of Millennium Development Goal-oriented trade policies in developing countries contributing to accelerating achievement of Millennium Development Goals in the context of multiple and interrelated development challenges |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To support developing countries in building the capabilities to elaborate coherent MDG-oriented trade policy frameworks that set the basis for the development, adoption and implementation of their own best-fit trade policies. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 42.0 Consultants 220.0 Travel 104.0 Operating expenses 88.0 Workshops 240.0 Total 694.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance related to preparation and review of national trade policy frameworks under activity (i) ($7,000 per work month x 6 work month) = $42,000 Consultants International consultants ($50,000): In support of activity (a), 1 MDG oriented trade policy training package by (1 consultant for $15,000 for one month plus travel and DSA of $5,000) = $20,000; Formatting of the training package in user friendly module by (1 consultant for $5,000) = $5,000; Adaptation of the training package to specific country situations at ($2,500 per country for a total of 10 countries.) = $25,000 National / Regional consultants ($150,000): 10 comprehensive MDG-oriented national trade policy frameworks produced for 10 countries by national consultants (activity (b)). ($2,500 per consultant per month for six months x 10) = $150,000 Consultant for external evaluation: ($20,000) Travel Organizing and servicing the 10 national and 2 interregional workshops under activity (b) and (c); providing 4 advisory services under activity (d) and 10 training services under activity (e). A total of 26 missions at an average cost of $4,000 per mission (travel and DSA) ( 26 x $4,000) = $104,000 Operating expenses Communication expenses, editing, translation from English into French or Spanish or vice-versa, and printing and supplies in support of activities (a), (b) and (c) Seminars and Workshops National workshops ($90,000): In support of activity (b), (10 national consultative and validation workshops, on the national “best fit” trade policy frameworks, with each workshop costing $9,000 for conference facilities) = $90,000; Interregional workshops $150,000): In support of activity (c), two interregional workshops of 3 days comprising: (i) 1 workshop of 5 countries with 3 participants per country ($4,000 per participant including DSA) = $60,000 + conference facilities ($15,000) = $75,000; (b) 1 workshop of 5 countries with 3 participants per country ($4,000 per participant including DSA) = $60,000 + conference facilities ($15,000) = $75,000 |  | 42 000 220 000 104 000 88 000 240 000 |

| L. Addressing the impact of trade and trade agreements on employment in developing countries |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012– 2015 |  |
| Objective To strengthen the link between international trade and employment generation in selected developing and least-developed countries and to support the implementation of trade and development policies with impact on productive employment and contribution to MDGs. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 67.0 Travel 35.0 Operating expenses 15.0 Workshops 115.0 Total 232.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants National consultants ($40,000): In support of activity ((a): four national and regional case studies used for technical cooperation. Consultant costs ($2,500 for 4 month x 4) = $40,000 National consultant for external evaluation: ($2,000) International consultants ($25,000): In support of activity (b): two global studies on the agriculture and services sectors and employment generation. Consultant costs ($12,500 for one month x 2) = $25,000 Travel In support of activity (c): Travel to the interregional workshops, advisory missions and presentation of findings at international conferences on the subject. Estimated 7 missions cost $5,000 (DSA and travel) = $35,000 Operating expenses In support of activities (c), (d) and (e): Communication expenses, editing, translation and printing Workshops In support of activity (c): Two interregional workshops of 2-3 days with 15 participants of which 5 are locals ($5,000 per non-local participant including DSA) x 10 x 2) = $100,000; Conference facilities ($7,500 x 2) = $15,000 |  | 67 000 35 000 15 000 115 000 |

| M. Strengthening of capacities of trade and planning ministries of selected LDCs to developing and implementing trade strategies that are conducive for poverty reduction |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: Jointly implemented by UNCTAD's Division for Africa, Least Developed Countries and Special Programmes and its Division on International Trade in Goods and Services, and Commodities |  | Duration: 2012 – 2015 |  |
| Objective: The project aims at strengthening the capacities of trade and planning ministries in selected LDCs to identify trade priorities as well as formulate and implement trade strategies leading to poverty reduction. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 55.0 Consultants 144.0 Expert Group 160.0 Travel 140.0 Operating expenses 22.0 Workshops 120.0 Total 641.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform the tasks related to the coordination and implementation of the national workshops, expert groups and national trainings, in support of activities (a), (c) and (d) Consultants National consultants ($102,000): 6 national consultants to assist select LDCs in formulating and implementing a trade strategy and developing trade policy framework and to participate in the sub-regional expert meetings, in support of activities (b) and (d) (6 consultants x 6 work months x US$2,000 per month = $72,000) + (6 consultants x $5,000 per travel to expert meeting = $30,000); International consultants ($30,000): 1 international consultant to further develop and adapt training material used in project S of the 7th Tranche and to participate in the expert group meeting as a resource person, in support of activities (b), (c) and (d). (1 consultant x 2 work months x $10,000 per month + travel to both expert meetings $10,000) = $30,000 Consultant for external evaluation: $12,000 Expert Group 2 subregional expert group meetings (one for the French-speaking LDCs and one for the English-speaking LDCs) organized by UNCTAD in two of the selected LDCs to discuss challenges, lessons learned, best practices, etc., in support of activity (d) (2 expert group meetings x $80,000 per meeting) = $160,000 Note: Travel and fees of consultants to participate in expert group meeting are covered under item 'Consultant'. This cost covers the organization and logistics arrangements of the expert group meetings and thus should be added to the item 'Workshops' in the summary table Travel Travel of UNCTAD staff to coordinate and participate as resource persons in workshops (workshop to prepare development and implementation of trade strategy, validation workshop), in support of activities (a) (2 workshops in 6 countries x $5,000 per travel) = $60,000; Travel of UNCTAD staff to provide a national training module, in support of activity (c) (Training module in 6 countries x $5,000 per travel x 1 staff) = $30,000; Travel of UNCTAD staff to expert group meetings, in support of activity (d) (2 staff x 2 meetings x $5,000 per travel) = $20,000; Travel of UNCTAD staff to provide advisory services on trade policy formulation and implementation, in support of activity (e) (1 mission per country (6) x $5,000 per travel) = $30,000 Operating expenses Communication expenses in support of activities (a), (d) and (f) and Editing and printing in support of activity (e) Seminars and Workshops 12 national workshops on trade strategy and policy (2 per beneficiary country), in support of activity (a): (2 workshops per country x 6 x $10,000 per workshop) = $120,000 |  | 55 000 144 000 160 000 140 000 22 000 120 000 |

| N. Building national capacities for promoting foreign direct investment in green and other growth sectors |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen developing countries’ capacity to attract and benefit from FDI in green and other growth sectors to create employment, promote agricultural development, and reduce poverty. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 40.0 Consultants 154.0 Contractual services 50.0 Travel 80.0 Operating expenses 35.0 Workshops 102.0 Total 461.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance 4 months, ad hoc assistance to conduct background research and organize advisory missions and capacity-building activities: ($10,000 x 4) = $40,000 Consultants International consultants ($120,000): 8 work months for advisory work, the design and delivery of capacity-building activities and for setting up the global online network on green FDI, in support of activities (a), (b), (c), and (d): Consultancy: ($10,000 x 8) = $80,000. Travel Consultants: ($5,000 x 8) = $40,000 National consultants ($24,000): 8 work months as part of teams providing advisory services and training in support of activities (a), (b) and (d): ($3,000 x 8) = $24,000 Consultant for external evaluation: $10,000 US$ 10,000 Contractual services Contractual services with local and regional institutions to support activity (d): $20,000; Establishment of the online network in support of activity (c): $30,000 Travel UNCTAD Staff: 10 travel to provide ad hoc advisory services to IPAs and to organize and deliver training in support of activities (a) and (d): ($6,000 x 10) = $60,000; Regional Commission staff / other UN staff: 5 travel arrangements to assist in the delivery of advisory work and training seminars in support of activities (a) and (d): ($4,000 x 5) = $20,000 Operating expenses Translation, simultaneous interpretation and printing of advisory reports, practical advisory guides and training manuals in support of activities (a), (b) and (d): $35,000. Seminars and Workshops 3 seminars in support of activity (d) mobilizing 30 regional participants: ($3,000 x 30) = $90,000; 1 non-regional resource person per seminar: ($4,000 x 3) = $12,000 |  | 40 000 154 000 50 000 80 000 35 000 102 000 |

| O. Promoting sustainable business models for development: Investing in the poor, for the poor and with the poor |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To develop and promote a curriculum for sustainable business models for investing in, with and for the poor. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 99.0 Contractual Services 60.0 Travel 36.0 Operating expenses 37.0 Workshops 200.0 Total 462.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance GTA for developing methodology and assistance to organize and support the preparation of the curriculum and the implementation of the first pilot course in support of activities (a), (c) and (d): ($6,000 x 5 work months) = $30,000 Consultants International consultants: for designing and participating in the pilot delivery of a business school course on "investing in the poor" in support of activities (a), (b) and (c): ($9,000 including travels x 6 work months) = $54,000 National Consultants: For the fine-tuning and the finalization of the curriculum to specific regional and cultural conditions in support of activities (a), (c) and (d): ($6,000x 6 work months) = $36,000; Consultant for external evaluation $9,000 Contractual services Contractual services with eight institutions of higher learning for implementing workshops and pilot courses in support of activities (c): (workshops and fine-tuning); and (d): (implementation of a first pilot courses ) ($7,500 x 8) = $60,000 Travel 8 travels by international UN staff to organize and coordinate 3 workshops and 5 pilot courses in support of activities (b) and (d): ($4,500 x 8) = $36,000 Operating expenses Translation, simultaneous interpretation and printing of training manuals in support of activities (a) and (c): $25,000; Communications costs in support of activities (a), (b) and (e): $6,000 Supplies in support of activities (a), (b) and (d): $6,000 Workshops Three seminars (1 in Spanish, 1 in English and 1 in French) in support of activity (b) = $50,000; 5 regional workshops (2 in Africa, 1 in Latin America, 1 in Asia, 1 in Oceania) in support of activity (c): ($2,000 x 15 participants x 5 workshops) = $150,000 in support of activity (d) |  | 30 000 99 000 60 000 36 000 37 000 200 000 |

| P. Strengthening pro-growth macroeconomic management capacities for enhanced regional financial and monetary cooperation among selected countries of Latin America and the Caribbean and West and Central Africa |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: Strengthening pro-growth macroeconomic management capacities for enhanced regional financial and monetary cooperation among selected countries of Latin America and the Caribbean (LAC) and West and Central Africa (WCA). |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 50.0 Consultants 165.0 Travel 80.0 Contractual services 8.0 Operating expenses 2.0 Workshops 250.0 Total 555.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform research, drafting and editing tasks toward the publication envisaged as activity (d) (seven work-months at P-2 level) Consultants International consultants: International experts to carry out field tasks of data collection, analysis and training under the guidance of UNCTAD staff: (Eight work-months of experts for activities (a), (b), (c) and (e) x $7,500) = $60,000; Regional consultants: Regional experts to carry out field tasks of training services under the guidance of UNCTAD staff. (Eight work-months of experts for activities (e) and (f) x $5,000) = $40,000; National consultants: National experts to assist in data collection, analysis, training tasks: (Twelve work-months of experts (6 from each region) for activity (b) and (f) x $4,170) = $50,000; Project evaluation International consultant, 1 month + travel: $15,000 Travel 8 field missions to LAC ($45,000) and 8 missions to WCA ($35,000) for activities (a), (b) (c) and (f) Contractual services: Printing services for the publication: activity (b) Operating expenses: Postage and communication costs: activities (b) and (c) Seminars and Workshops Study tours ($95,000): Two study tours in support of activity (d) for 8 participants to Asia, and 4 participants to West Africa for a total of $95,000; Regional seminars/workshops ($155,000): 1 regional seminar/ training workshop in LAC in support of activities (c) and (f) for 12 participants estimated at $55,000; 1 regional seminar/training workshops in CWA in support of activities (c) and (f) for 12 participants estimated at $40,000; 1 Ad hoc expert group to conclude project activities in support of activities (b) and (c) for 12 participants estimated at $60,000 |  | 50 000 165 000 80 000 8 000 2 000 250 000 |

| Q. Mainstreaming ecosystem service into country’s sectoral and macroeconomic policies and programmes |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNEP |  | Duration: 2012 – 2015 |  |
| - Objective: To develop national capacity to integrate ecosystem services considerations into the macroeconomic policies and programmes of the selected developing countries |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 80.0 Consultants 130.0 Expert Group 30.0 Travel 32.0 Contractual Services 145.0 Operating expenses 15.0 Workshops 110.0 Total 542.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance A provision of $80,000 is required to cover part of the costs for a full time temporary assistant to perform the tasks of supporting the overall implementation of the project, particularly administration and fund management, technical inputs and overseeing monitoring and evaluation of the project: (24 work months x $3,333 per work month) Consultants International consultant ($60,000): In support of activity (d): for the task(s) of technically supporting the overall coordination of the project, advising/supporting national consultants in preparation and implementation of workshops and research as well as outreach component: (5 work months/year x 2 years x $5,000 per month = $50,000) + ($10,000 for consultant travel = $10,000); National / Regional consultants ($50,000): In support for activity (b): for the task(s) of establishing national networks of experts and policy makers, preparing and implementing workshops and Participatory Reviews of integrated assessments as well as outreach. (10 work months x $2,000 per month x 2 consultants) = $40,000) + ($10,000 for consultant(s) travel = $10,000); Final evaluation: External evaluation after the project = $20,000 Expert Groups A provision of $30,000 is required to cover travel cost and other allowances needed for the participation of the members of national expert groups in one consultation per country in support for activity (c): ($15,000 per meeting x 2 countries) Travel A provision of $32,000 is required in support for activities (b), (c), (d) and (e): for missions by international and regional staff for the organization and participation in experts groups, training workshops, Participatory Reviews of integrated assessments and other relevant activities: International UN Staff: (4 missions) by international UN staff for the purpose of facilitating establishment of national expert groups, workshops and study tours as well as outreach and linking up national expert groups ($5,000 average mission cost x 4 missions) = $20,000; Regional staff/ other UN staff: (4 missions) by regional UN staff for the purpose of facilitating contacts with national experts and governments ($3,000 average mission cost) x 4 missions) = $12,000. Contractual Services In support of all activities $10,000 for lead national institutions to make arrangements for the workshops and make other necessary arrangements such as recruitment of national consultants, experts, overseeing national level outreach activities, etc.; Case studies in (two countries x $67,500 per country) = $135,000 for conducting economic valuation, ecosystems accounting, identification of key indicators to be included in national monitoring systems and development of recommendations and action plans to mainstream ecosystem service considerations into development planning processes including those that address poverty alleviation. Operating expenses Communications for developing a project website, brochures and other outreach materials to disseminate the information on the project $15,000, in support of activities (a) to (e) Seminars and Workshops In support of activities (c) and (e): 1 training workshop on tools and methodologies per country (2 countries x $40,000) = $80,000; 1 policy dialogues meeting and outreach event per country (2 countries x $15,000) = $30,000. |  | 80 000 130 000 30 000 32 000 145 000 15 000 110 000 |

| R. Integrating environmental sustainability in the UN Development Assistance Frameworks (UNDAFs) and UN common country programming processes |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNEP |  | Duration: 2010 – 2013 |  |
| Objective: To strengthen the capacities of selected UNCTs and national institutions to integrate environmental sustainability in the preparation (5 countries) and implementation (5 countries) of the UNDAF and national development strategy. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 65.0 Travel 90.0 Contractual services 383.5 Workshops 2.5 Total 541.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants Local consultants ($50,000): Activity (b): Prepare environmental assessment and information to inform the country analysis and the preparation of the UNDAF and national development strategy in 3 countries (3 countries x $15,000) = $45,000; Activity (c): Deliver a training course to 5 UNCTs and government partners on integrating environmental sustainability in the country-level planning processes (5 countries x $1,000) = $5,000; International consultants ($15,000): All activities: Conduct the final evaluation of the project Travel All activities: 3 missions per year to 10 countries to manage and oversee the implementation of the project (3 missions x 10 countries x $3,000) = $90,000 Contractual services Activity (a): Deliver the UNDAF outputs for which UNEP is responsible in 5 countries (building on results under the 7th tranche of the Development Account) to strengthen the national capacities to achieve the MDG7 (5 countries x $70,700) = $353,500; Activity (b): Prepare environmental assessment and information to inform the country analysis and the preparation of the UNDAF and national development strategy in 2 countries (2 countries x $15,000) = $30,000 (in Europe and Latin America and Caribbean region, the project will sub-contract national institutions, eg. National Academy of Science to deliver this activity because of their specialised expertise in environmental assessments, network of national institutions, credible track record and engendering national ownership of the assessments) Seminars and Workshops Activity (b): Hold a meeting with the UNCT and government partners to prepare the environmental assessment and information (5 countries x $500) = $2,500 |  | 65 000 90 000 383 500 2 500 |

| S. Development of a review system for the effective national implementation of Multi-lateral Environmental Agreements |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNEP |  | Duration: 2012 – 2015 |  |
| Objective: To enhance the capacity of national Governments to implement their environmental obligations and achieve the environmental and developmental goals, targets and objectives agreed under Multilateral Environmental Agreements. |  |  |  |
| Summary budget (Thousands of United States dollars) Expert Group 100.0 Travel 83.0 Contractual Services 160.0 Workshops 200.0 Total 543.0 | ## Detailed budget (US dollars) |  |  |
|  | Expert Group In support of activity (a): A small Expert Group will be formed to design the methodology and outline for the review system of MEAs envisaged under the project. Costs covered under this item include travel and meeting expenses for two physical meetings, one to discuss and approve the methodology for the national reviews, and one concluding meeting to develop conclusions and guidelines for further reviews to be undertaken by other countries. Additional meetings of the group will be conducted via video- or tele-conferencing (2 x $50,000) = $100,000 Travel of staff In support of activity (b): travel in the implementation of the project (e.g. travel to the pilot countries). Envisaged are 3 - 4 missions per country at an estimated cost of $3,000 – $5,000 each. Contractual Services In support for activity (b): contracts with NGOs and institutions assisting in the implementation of the project that will focus in three major topics: Environmental Law Institute, International Network for Environmental compliance and Enforcement, and Working Group on Environmental auditing ($50,000 x 3 = $150,000); publications to publicize the findings of the project = ($10,000) Seminars and Workshops In support of activity (c): will cover the organization of national workshops to assess the findings of the review and address the capacity gaps identified. Envisaged is one workshop per country at an estimated cost of ($40,000 x 5 countries) = $200,000, to discuss the findings of the review process and provide targeted capacity building and awareness rising for national stakeholders. |  | 100 000 83 000 160 000 200 000 |

| T. Strengthening the capacities of the International Conference on the Great Lakes Region (ICGLR) member states to address the land and property issues of Internally Displaced Persons (IDPs) and refugees, with a specific emphasis on women's land and property rights |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UN-HABITAT, in cooperation with the International Conference of the Great Lakes Secretariat (ICGLR), the African Union and the Economic Commission for Africa |  | Duration: 2012 – 2015 |  |
| Objective: To increase Government and practitioner capacity to address land and property issues of displaced persons and refugees in selected Great Lakes States. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 138.0 Travel 18.0 Contractual services 184.0 Workshops 112.0 Total 452.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International Consultants ($96,000): International consultant to develop legal and institutional assessment tool and support national/regional consultants in delivery of activities (a) to (e): (8 work months at $10,000 per work month ) = $80,000 + $16,000 travel = $96,000; National/Regional Consultants ($42,000): Regional training specialist for activity (c) material development and training delivery (2 work months at $5,000 per work month) = $10,000 + $5,000 for travel) for total of $15,000; Regional legal specialist to prepare activity (a): legal and institutional synthesis report (1 work month at $5,500 per work month + $1,500 for travel) for total of $7,000; National gender experts to provide inputs to activities (a) to (e): (4 experts x 1 work month per expert at $5,000) = $20,000 Contractual services 4 contracts to national organisations for activity (a) state of land and property rights of IDPs and refugees including local travel (4 contracts at $10,000 per organisation) = $40,000; 4 contracts to local organisations/firms to undertake the legal and institutional assessment for the domestication of the land and property protocols (4 contracts at $25,000 per country) = $100,000); 1 contract to a regional organisation for activity (e) the production and translation (English and French) of a variety of information and outreach materials $15,000; 1 contract to evaluate activities (a) to (e) including travel to up to 2 countries $9,000; 1 contract to a regional publishing firm for printing and dissemination of materials produced under activities (a) to (e): $20,000. Travel of staff In support of activities ((d) and (e): 7 one week missions to support trainings and country assessments (around $2,600 per mission ) Seminars and Workshops Four 2 day trainings on land and property rights for activity (d): ($20,000 per training x 4) = $80,000; Four one-day validation workshops for the findings from the land and property study and the legal and institutional assessment ($8,000 per workshop x 4) = $32,000 |  | 138 000 184 000 18 000 112 000 |

| U. Strengthening capacity of policy makers in South East Asia for promoting policies and developing plans for improved wastewater treatment and reuse in urban and peri-urban areas |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UN-HABITAT and ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: To improve wastewater management and reuse in South-East Asia, with a priority focus on Lao PDR, Cambodia and Viet Nam |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 62.5 Travel 32.5 Contractual Services 133.0 Workshops 90.0 Total 348.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance (in support of activities A1, A2 and A3 (12 months x $2,500 per month) = $30,000 Consultants International consultants for preparing background papers and promotional material on decentralized wastewater management in support of activity (a): (4 months x $5,000 = $20,000), for preparing capacity building materials for the centres of excellence on the promotion of DEWATS in support of activity (b): (3.5 months x $5,000 = $17,500), for project evaluation in support of activity (c): ($5,000 x 3 months = $15,000) and for carrying out the project evaluation (1 month x $10,000) Travel Identification of good practices in three countries (Lao PDR, Cambodia and Viet Nam) on sustainable and replicable DEWATS solutions, to be promoted through the Seminar in support of activity (a) (3 trips x $3,000 = $9,000); two trips to each Centre of Excellence to support capacity building activities (4 trips x $2,000 = $8,000) and one coordination meeting between UN-HABITAT and ESCAP ($2,000) in support of activity (b); travel of regional technical advisor of UN-HABITAT ($6,000) for project monitoring in the 3 countries and travel of UN-HABITAT country staff members ($7,500) in support of activities (b) and (c) Contractual Services ESCAP to use approximately $3,000 for printing of materials in support of activity (a); approximately $35,000 for a grant to a local partner who will engage in preparing training course and publication, in support of DEWATS Centres of Excellence for activity (b); UN-Habitat to use $95,000 for a DEWATS in support of activity (c) Seminars and Workshops One (40 people) awareness raising seminars for policy makers and planners (40 x $750 = $30,000), to widely disseminate good practices and promotional material, with a guidance manual on DEWATS in the Mekong region in support of activity (a); 4 trainings for the Centres of Excellence (2 Centres x 2 x $10,000 = $40,000) and support for study tours to facilities in support of activity (b); 3 national workshops (3 x $5,000 = $15,000) and 1 regional workshop in support for activity (c) for ($5,000) |  | 30 000 62 500 32 500 133 000 90 000 |

| V. Integrating crime, corruption, drugs and terrorism related issues into the preparation of national development plans and processes |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: UNODC |  | Duration: 2012 – 2015 |  |
| Objective: To ensure that the issues of crime, corruption, drugs and terrorism are integrated into the preparation of national development plans and processes. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 50.0 Consultants 134.0 Travel 70.0 Contractual Services 218.0 Operating expenses 15.0 Communication 24.0 Supplies 15.0 Workshops 124.0 Total 650.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance on project activities: 10 work months of staff to carry out the implementation of all of the activities (10 months x $5,000) = $50,000 Consultants Regional consultants to undertake assessments in support of activity (a), (b) and (c): (12 work months x $5,000 per month x 2 persons) = $120,000 Consultant for final evaluation: $14,000 Travel of staff Travel within region in support of activities (a), (b) and (d) = $70,000 Contractual Services Contractual services with local institutions in support of (a), (b) and (c) to be identified (including think tanks and academic institutions for the development of guidance notes and tools to be used as UNODC reference documents for field offices ) = $218,000 Operating Expenses In support of all activities Communication In support of activities (a), (b), (c) and (d) = $24,000 Supplies In support of (a), (b), (c), and (d) = $15,000 Seminars and Workshops Organization of at least 8 national workshops in support of activities (b) and (d): ($15,500 per workshop x 8 workshops) = $124,000 |  | 50 000 134 000 70 000 218 000 15 000 24 000 15 000 124 000 |

| W. Strengthening the capacity of Civil Registration and Vital Statistics (CRVS) Systems in Africa to produce continuous and reliable indicators for measuring progress on the development agenda |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECA in collaboration with ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: The overall objective is to build the capacities of national governments in Africa and Asia and Pacific regions to strengthen the civil registration and vital statistics systems for efficient delivery of legal and administrative services and improve vital statistics to help monitor the progress towards achievement of the targets under the internationally agreed development goals including the MDGs. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 56.0 Consultants 150.0 Expert groups 200.0 Travel 60.0 Contractual services 35.0 Operating expenses 21.0 Workshops 160.0 Total 682.0 | ## Detailed budget (US dollars) |  |  |
|  | General temporary assistance Two persons to be recruited temporarily for the duration of 6 months each. Staff will provide research and technical assistance on all activities of the project (6 work months x $3000 per month x 2 persons) = $36,000; Salaries of support staff (8 months x $500 per month) = $4,000; Evaluation: An external consultant ($5,000 per month x 2 months) = $10,000 + $6,000 for travel) = $16,000 Consultants In support activities (a), (b) and (e): Two consultants with expertise in CRVS to support EGM, Workshops and Inter-regional meetings, reviewing of the manuals and training materials (Consultancy fee: ($5,000 x 4 months x 2 = $40,000) + (travel $5,000 x 2 = $10,000) for a total of $50,000; Two consultants to develop of guidelines and operational manual (Consultancy fees: $5,000 x 4 months x 2 = $40,000) + (travel $5,000 x 2 = $10,000) for a total of $50,000; Two consultants to prepare training material, and handbook (Consultancy fees: $5,000 x 4 months x 2 = $40,000) + (travel $5000 x 2 = $10,000) for a total of $50,000 Expert groups In support of activity (a): Two expert group meetings for the validation of the manuals, guides and training materials on CRVS ($2,000 per participant x 20 participants x 2) = $80,000; Two Interregional meetings to share experience and review the achievements and validate the outcomes ($4,000 per participant x 15 participants x 2 meetings) = $120,000 Travel of staff In support of activities (a) and (b): 12 missions by staff for the purpose of coordinating the organization of the workshops, EGMs and country activities ($2,500 average mission cost x 12 missions x 2 persons) = $60,000 Contractual Services In support of activities (c) and (d): Printing and publishing of the training material and analytical tools = $10,000; Translation of documents into French and Arabic = $10,000; Interpretation services in English, Arabic and French during workshops and EGMs = $15,000 Operating expenses In support of activities (c) and (d): Communications = $9,000; Supplies = $12,000 Workshops In support for activity (b): 4 capacity building workshops ($ 2,000 per participant x 20 participants x 4 workshops) = $160,000 |  | 56 000 150 000 200 000 60 000 35 000 21 000 160 000 |

| X. Strengthening Capacity of African Countries to Promote the Use of Renewable Energy to Achieve Sustainable Development and Poverty Reduction |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECA, in collaboration with ESCAP, ECE, DESA, ECLAC, and ESCWA |  | Duration: 2012 – 2015 |  |
| Objective: The main objective of the project is to build the capacity of sub-Saharan African countries to reduce energy poverty by facilitating access to renewable and clean energy |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 35.0 Consultants 166.0 Expert groups 70.0 Travel 79.0 Operating expenses 25.0 Workshops 328.0 Total 703.0 | ## Detailed budget (US dollars) |  |  |
|  | General temporary assistance As part of the implementation of the Development Account, the Subregional Offices will organize meetings, workshops, seminars for which simultaneous interpretation is necessary in both English and French. This provision will enable the four Sores to engage freelance interpreters and translators (both in English and French) to service the meetings. Freelance translators will also be recruited to translate the documents for these meetings Consultants International consultants ($86,000): In support of activity (a): To be hired by ECA to conduct baselines studies and comparative analyses, develop training modules and materials at workshops, seminars and appropriate for a, and, provide other technical assistance in support of the activities under this project. (8 work months x $8,000 per month) = $64,000 plus $22,000 for travel totalling = $86,000; Regional/National Consultants ($80,000): In support of activity (a): To be hired by ECA to conduct primary research and review of case studies, adaptation of standards, and project selection criteria, contributions to base line studies and comparative analyses, delivery of training workshops, seminars and conferences in collaboration with international consultants, and support of sub-regional authority of country specific activities. (4 work months x $5,000 x 4 Consultants) = $80,000 Expert Group In support of activity (b): One (1) expert group meeting with 2 days duration: for 20 participants (five per Subregional Offices) is envisaged on institutional and policy frameworks for the development of renewable energies and energy efficiency at national and sub regional level. ($3,000 per participant x 20 participants x 1 expert group meeting) = $60,000 plus other costs of $10,000 for a total of $70,000 Travel In support of activities (b), (c) and (d): The planned budget is dedicated to trips for staff members: (i) to gather up-to-date information and data for the preparation of reports and other technical papers to meetings, workshops, and training courses; (ii) participation in expert groups, workshops, training seminars, and providing advisory services. Cost estimates: Travel and DSA = $79,000. Operating expenses In support of activities (a) to (d): The amount proposed is needed for postage, communications, printing of reports, supplies, materials and equipment. ($5,000 for each x 5 ) = $25,000 Seminars and Workshops Workshop ($148,000): In support of activity (c): for 30 senior government officers, representatives of national power production agencies, financial experts and independent experts on policies and programmes formulation/implementation to enhance Public Private Partnership for power supply, design bankable projects for energy efficiency financing and capacity building in accessing energy finance from different funding mechanisms and for the promotion of the design of models of energy efficiency and renewable energy investment frameworks in sub Saharan Africa. Duration: 2 days; Cost estimates: Travel & DSA: $138,000 and other costs: $10,000 Forum ($180,000): In support of activity (d): Sub Sahara African Forum on renewable energies for 50 participants including senior government policy makers, independent experts, researchers, manufacturers of RET, media, NGOs, IGOs for sharing best practices and experiences on renewable energies in sub Sahara Africa. Duration: 3 days; Cost estimates: Travel & DSA: $170,000 and other costs: $10,000 |  | 35 000 166 000 70 000 79 000 25 000 328 000 |

| Y. Capacity Building for risk and disaster management systems, through use of Information and Communication Technologies in Africa |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECA in collaboration with ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: The project aims to build capacity of African policy makers, experts and stakeholders working in the area of economic risks, Disaster risk reduction and management and emergency response related research and activities, through exploitation of ICTs and online platforms for risk and disaster management, and their integration in national policies of member States. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 42.0 Consultants 211.0 Travel 61.6 Operating expenses 23.4 Workshops 351.0 Total 689.0 | ## Detailed budget (US dollars) |  |  |
|  | General temporary assistance Five persons each to be recruited temporarily at ECA HQ and Subregional Office for North Africa for the duration of the project. They will provide research and technical assistance on all activities of the project (24 work months x $350 per month x 5 persons) = $42,000 Consultants International consultant ($156,000): In support of activities (a) to (d): One senior international consultant who will undertake needs assessment and develop course framework on Risk Management and Disaster Risk Reduction (1 person x 7 work months x $7,000 per month) = $49,000; One international consultant to prepare and produce training manuals for onsite capacity building workshops on Risk Management and Disaster Risk Reduction (1 person x 6 work months x $5,000 per month) = $30,000; Two international consultants to serve as resource persons for onsite capacity building workshops on risk management and use of ICTs for Risk Management and Disaster Risk Reduction to be held in Addis Ababa, Kigali, Lusaka, Accra and Rabat. ($5,600 per session x 5) = $28,000; Two international consultants to translate documents produced from the various activities of the project from English to French and vice versa. (2 persons x 7 work months x $3,500 per month) = $49,000; National consultants ($40,000): In support of activities (a) to (d): One national consultant to develop an online platform for risk monitoring and watch (1 person x 4 work months x $5,000 per month) = $20,000; One national consultant to develop online versions of the three modules and delivery on the ECA’s online learning system as well as maintenance of the system (1 persons) x 4 work months x $5,000 per month) = $20,000; Regional Evaluation consultant ($15,000): In support of activities (a) to (d): One regional consultant to undertake evaluation of the project in line with the requirements of development account projects and dissemination of lessons learnt. (1 person x 1 work month x $15,000 per month) = $15,000 Travel of staff In support of activity (b): ECA staff for the organization of capacity building workshops and on the ground assessment of risk management activities in selected member States ($2,800 average mission cost x 11 missions x 2 persons) = $61,600 Operating expenses In support of activities (a) to (d): Communications = $5,400; Supplies = $7,000; Workshops Local Cost = $11,000 Workshops and Trainings In support of activity (b): One Training of Trainers workshop on the frameworks of the 2 modules in Addis Ababa ($2,575 per participant x 40 participants) = $103,000; One each awareness raising and sensitization workshop for policymakers / stakeholders per subregion in Kigali, Lusaka, Rabat and Accra ($1,550 per participant x 20 participants x 4 subregions) = $124,000; One each Training of Trainers workshop per subregion in Kigali, Lusaka, Rabat and Accra ($1,550 per participant x 20 participants x 4 sub-regions) = $124,000 |  | 42 000 211 000 61 600 23 400 351 000 |

| Z. Strengthening capacities for the development of regional agricultural value chains in Africa |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECA |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen the capacities of policy makers and other key stakeholders to develop competitive regional agricultural value chains in Africa. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 12.0 Consultants 190.0 Travel 25.0 Contractual services 47.0 Workshops 225.0 Total 499.0 | ## Detailed budget (US dollars) |  |  |
|  | General temporary assistance A provision of $12,000 is required to cover: -In support of all activities: General temporary assistance (full-time) for 12 work months (General Service Staff) = $12,000 Consultants In support of activities (a) to (e): National/regional consultants for the task(s) of facilitating activities of national / regional organisations and conducting the regional level assessment, and organization of workshops and meetings. Writing reports and projects documents: 8 regional consultants (Agricultural Economist, Geographic Information System specialist, Value Chain Expert, and Environmentalist) for 4 work months @ $5,000 per month: 4 for COMESA and 4 for ECOWAS = ($5,000 x 8 x 4) =$160,000; Travel costs for consultants ($2,500 x 8) = $20,000; One Senior Consultant to consolidate and finalize the assessment reports: $10,000 for 1 work-month Travel of staff In support of activity (a): Staff of ECA’ subregional offices to participate in workshop planning and implementation activities ($2,500 per person x 2 persons) = $5,000; In support of activity (b): Staff of ECA to help organize and attend validation and training workshops ($2,500 x 2 persons x 4) = $20,000 Contractual services In support of all activities: Translate documents into French ($15,000); In support of all activities: Interpretation for workshops ( $32,000) Seminars and Workshops In support of activities (c), (d) and (e): Two validation workshops: Travel and DSA and approximately 15 participants per Regional Economic Communities (REC): Travel and DSA ($2,500 x 15 x 2 ) = $75,000; Two training workshops at the Subregional Offices ( 1 in Niamey, 1 in Kigali) for 15 participants per REC: Travel and DSA ($2,500 x 15 x 2) = $75,000; Public-Private Partnership Policy Dialogue Forum for 30 participants: Travel and DSA ($2,500 x 30) = $75,000 |  | 12 000 190 000 25 000 47 000 225 000 |

| AA. Strengthening the capacities of developing countries and countries with economies in transition to facilitate legitimate border crossing, regional cooperation and integration |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECE in cooperation with ESCAP, ESCWA, ECA, and ECLAC |  | Duration: 2012– 2015 |  |
| Objective: To strengthen the capacities of developing countries and countries with economies in transition to facilitate border crossing, by means of increased exchange of secure electronic information between Customs administrations. |  |  |  |
| Summary budget (Thousands of United States dollars) General temporary assistance 27.0 Consultants 158.7 Expert group meetings 30.0 Travel 39.0 Contractual services 150.0 Operating expenses 17.3 Equipment and supplies 85.0 Workshops 243.0 Total 750.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance 25 per cent of an IT expert for 1 year in support of activity (b) (3 work months x $9,000 per month) = $27,000 Consultants International consultants ($96,000): for the development of the exchange platform in support of activity (b) (12 work months x $8,000 per month) Two national and/or regional consultants ($48,000): to deliver effective inputs at expert groups, workshops and seminars as well as to provide other technical assistance in support of activities (a), (b), (c) and (d) (6 work months x $8,000 per month) Consultant for final project evaluation: $14,700 One Expert Group In support of activity (a): ($1,500 per participant x 20 participants) Travel of staff 13 missions x (1 or 2 staff member per mission) by UN staff for conducting Expert Groups, workshops and seminars and provide technical assistance in support of activities (a), (c) and (d). ($3,000 average mission cost x 13 missions) = $39,000 Contractual services Contracts will be awarded to national companies to assist 5 selected Customs authorities in the linkage of national Customs systems with the exchange platform in support of activity (d): (5 x $30,000) = $150,000 Operating expenses Communications in support of activities (a), (b), (c) and (d) = $10,000; Supplies in support of activities (a), (b), (c) and (d) = $7,300 Equipment and Supplies The exchange platform will be supported by a secure IT infrastructure (servers and software) for activity (b) (Central servers and data storage ($60,000), and national servers in pilot countries ($25,000) = $85,000 Seminars and Workshops 5 national technical workshops in support of activity (d). ($1,000 per participant x 24 participants x 5 workshops) = $120,000; 1 seminar in support of (c): ($1,500 per participant x 50 participants) = $75,000; Translation of documentation and interpretation for Expert Groups, Workshops and seminars in support of activities (a), (c) and (d): (6 x $8,000) = $48,000 |  | 27 000 158 700 30 000 39 000 150 000 17 300 85 000 243 000 |

| AB. Promoting Energy Efficiency Investments for Climate Change Mitigation and Sustainable Development |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECE, in collaboration with ESCAP, ESCWA, ECA, ECLAC, DESA and UNIDO within the framework of UN-Energy |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen capacities of developing countries and countries with economies in transition to attract investments in energy efficiency and renewable energy projects in the context of climate change mitigation and sustainable development. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 215.0 Travel 120.0 Contractual services 150.0 Operating expenses 33.0 Workshops 732.0 Total 1 250.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International consultants ($100,000): International consultants to develop pre-feasibility studies for the energy efficiency projects for at least one targeted country from each region for investors’ consideration in support of activities and to deliver effective training modules at workshops and conference. (2 work months x $7,000 per month x 5) = $70,000; Travel of international consultants in support of activities (b) to (f): ($6,000 for consultant travel x 5) = $30,000; National / Regional consultants ($90,000): National consultants for tasks of conducting primary research and review of case studies, adaptation of standards and project selection criteria, contributions to comparative analysis, delivery of training workshops and conference in cooperation with international consultants, and support of country-specific in support of all activities: 2 work months x $3,000 per month x 15 countries) = $90,000; Consultant for final project evaluation: $25,000 Travel of staff (6 ECE missions + 12 other Regional Commissions missions, + 2 DESA missions) x (1 staff member per mission) by international UN staff for the purpose of organizing and servicing workshops, policy seminars and training, in support of activities (b) to (f): ($6,000 average mission cost x 20 missions) = $120,000 Contractual services Contracts (15 contracts to be implemented by the RCs): Up to 15 contracts will be awarded to national entities to undertake comprehensive case studies on experience of policy reforms in support of activity (c). ($10,000 x 15 countries from RCs) = $150,000 Operating expenses Communications (40 per cent for ECE, 40 per cent for the other RCS, 20 per cent for DESA): In support of all activities: $10,000; Supplies (40 per cent for ECE, 40per cent for the other RCS, 20 per cent for DESA); In support of all activities: $23,000. Seminars and Workshops Workshops (one to be implemented by each Regional Commissions): 5 regional workshops on case studies in support of activity (c). ($2,000 per participant x 15 participants x (5 workshops) = $150,000; Seminar (to be implemented by each RC): 5 regional policy seminars in support of activity (d). ($2,000 per participant x 15 participants x 5 seminars) = $150,000; Training (to be implemented by Regional Commissions): 10 Trainings in support of activities (b) and (e): (two in each region): ($2,000 per participant x 15 participants x 2 trainings x 5 regions) = $300,000; Workshop (to be implemented by ECE): 1 global workshop organized by ECE in support of activity (e): ( $2,200 per participant x 60 participants) = $132,000 |  | 215 000 120 000 150 000 33 000 732 000 |

| AC. Towards productivity convergence: Trade, financing and technology for small-scale enterprises |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECE jointly with ESCAP, ESCWA, ECA, ECLAC, and UNIDO |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen capacities of developing countries and countries with economies in transition to attract investments in energy efficiency and renewable energy projects in the context of climate change mitigation and sustainable development. |  |  |  |
| Summary budget (Thousands of United States dollars) Consultants 160.0 General temporary assistance 35.0 Travel 80.5 Contractual services 15.0 Operating expenses 24.5 Workshops 260.0 Total 575.0 | ## Detailed budget (US dollars) |  |  |
|  | Consultants International consultants ($70,000): Two international consultants will prepare four case studies under activity (c); 12 work-months x $5,000 per month) = $60,000; and training materials under activity (d); (2 work-months x $5,000 per month) = $10,000; National consultants ($78,000): Will participate in the preparation of the case studies under activity (c): (4 work-months x $5,000 per month) = $20,000; and assist in the organization of the national training workshops under activity (e): (4 half work-months x $5,000 per month) = $10,000; Two international consultants and four national consultants participate as trainers in the four workshops under activity (e); (4 half work-months x $5,000 per month) = $20,000; and present technical findings at the two high-level forums under activity (f): ($3,500 per person x 8 individual missions) = $28,000 Consultant for final evaluation: $12,000 General temporary assistance Hiring of a statistical assistant to help in the development of integrated data bases and preparation of the case studies under activities (c)and (d): (10 work-months x $3,500 per month) = $35,000 Travel of staff To participate in the field missions in the context of the preparation of the case studies in support of activity (c), to attend the four national training workshops in support of activity (d) and provide advisory services upon request. Travel of staff from UNCTAD, ILO and ESCAP to 4 workshops and 2 sub-regional meetings ($3,500 per person x 23 individual missions) = $80,500 Contractual services In support of activities (d) and (g): Will be used for the translation of training material from English to Spanish Operating expenses To finance the edition of documents and publications $10,000; and printing and distribution $14,500 in support of activities (d), (e), (f) and (g) Seminars and Workshops This should finance the national training workshops (activity e): (4 workshops x $ 25,000) = $100,000 and the organization of two sub-regional high-level meetings (activity f): travel of participants to sub-regional meetings: (2 meetings x $80,000) = $160,000 |  | 160 000 35 000 80 500 15 000 24 500 260 000 |

| AD. Towards a Low Carbon Economy in Latin America: Policy Options for Energy Efficiency and Innovation |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECLAC |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen the capacity of Latin American and Caribbean national governments to establish a path to low-carbon economic growth, through energy efficiency policies and measures, with particular attention to innovation policies. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 172.0 Travel 91.0 Operating expenses 21.0 Workshops 164.0 Total 478.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance To support four training workshops in the Latin America and the Caribbean (LAC) region and one workshop in the European region, the development of a regional network of energy efficiency practitioners in participating countries, and a regional meeting on low carbon economic recovery and growth in support of activities (e), (g) and (h): (10 work-months x $3,000 per month ) = $30,000 Consultants In support of activity (d): It is relevant to underline the difference in scope and objective of international and national consultancies: the former will be mainly dedicated to transferring the knowledge and expertise regarding the state-of-the-art in modern energy efficiency policy instrument. The latter, will take advantage of this knowledge transfer and focus their action in supporting the creation and management of national databases: International consultants ($100,000): For the construction of a database to evaluate the results of energy efficiency initiatives, the construction of a database to evaluate the impact of alternative public policies, training workshops in 4 countries of the LAC region and one workshop in the European region in support of activities (a) and (e): (12 work-months x $5,000 per month) = $60,000; For the estimation of the "capturable potential benefit" of energy efficiency policies (activity b) (4 work-months x $5,000 per month) = $20,000; For the provision of technical assistance to four countries in support of activity (f) (4 work-months x $5,000 per month) = $20,000; Consultant for final evaluation: $12.000 National consultants ($60,000): For the construction of a database to evaluate the results of energy efficiency initiatives and the construction of a database to evaluate the impact of alternative public policies activity (a): (14 work-months x $3,000 per month) = $42,000; For the estimation of the "capturable potential benefit" of energy efficiency policies in support of activity (b): (2 work-months x $3,000 per month) = $6,000; For the development of the databases mentioned in support of activity (a) coordinated with national authorities in four countries and two countries in the ECE region in support of activity (d): (2 work-months x $3,000 per month) = $6,000; For the development of a regional network of energy efficiency practitioners in participating countries in support of activity (g): (2 work-months x $3,000 per month)= $6,000 Travel of staff Travel to support the construction of databases, to evaluate the results of energy efficiency initiatives and evaluate the impact of alternative public policies on income, training workshops in 4 countries of the LAC region and one workshop in the European region, provision of technical assistance to 6 countries on the design and implementation of low carbon policies, a regional meeting to promote regional collaboration and information exchange on low carbon economic recovery and growth in support of activities (a), (d), (e), (f) and (h): ($3,500 per person x 26 individual missions) = $91,000 Operating expenses Publication of a document containing the main findings of the project in support of activity (c) Seminars and Workshops Training workshops in four countries of the LAC region and one workshop in the European region in support of activity (e) 5 meetings. It is expected to count on an average of 15 to 20 local participants (no travel cost) at each national workshop, with an average of operational expenses of $8,000 per workshop (4 workshop x $ 8,000) = $32,000. These costs are mainly related to the rental of conference venue and related expenses. In the case of the workshop that will be carried out in a European country (most probably, Belgium), the number of Latin American participants which will travel to Europe would be 12 (12 participants x $4,000) = $48,000 plus $10,000 in conference-related expenses (total for the European workshop) = $58,000; A regional seminar/workshop on low carbon economic recovery and growth under activity (i): Is it s expected to host 20 high-level governmental representatives from 10 region’s countries, financing their travel and per-diems (20 participants x $3,000) = $60,000 plus local conference-related expenses of $14,000 (total for the regional seminar) = $74,000 |  | 30 000 172 000 91 000 21 000 164 000 |

| AE. Time for equality: Strengthening the Institutional Framework of Social Policies |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECLAC, in collaboration with ESCAP and ESCWA |  | Duration: 2012 – 2015 |  |
| Objective: To promote social policies and institutional arrangements in countries of the Latin America and Caribbean, the Western Asian and the Asia Pacific regions, aimed at reducing inequality and social exclusion in accordance with MDG 1 |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 57.0 Consultants 241.0 Expert Group meetings 30.0 Travel 78.0 Contractual Services 20.4 Operating expenses 24.6 Study tours 35.0 Workshops 175.0 Total 661.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Assistance for project monitoring and support, research assistance in support of activity (a), web managing in support of activities (b) and (c), data entry in support of activity (c), conference support of activities (e), (f), and (g): (12 work months x $4,750 per month = $57,000) Consultants International ($113,000): Preparation of studies in collaboration with national consultants in support of activity (a) and holding expert group meeting in support of activity (g): (3 consultants x 5 months x US$6,000 per month) = $90,000 and $10,000 for consultants travel; International consultant for evaluation of the project ($13,000); National ($128,000): National consultant for maintaining and developing the website and electronic forums, in support of activity (b): (10 work months x $4,000 per month) = $40,000; National consultant for maintaining and expanding the web-based database, in support of activity (c): (10 work months x $4,000 per month) = $40,000; National consultants for preparation of studies for activity (a): (3 consultants x 4 months x $4,000 per month) = $48,000 Expert Groups Interregional expert group meeting in support of activity (g): ($3,000 per participant x 10 participants) = $30,000 Travel of staff For organizing, coordinating and participating the national workshops in support of activity (e): (8 trips x $3,000) = $24,000, the regional workshops in support of activity (f): (8 trips x $3,000) = $24,000 and the inter-regional expert group meeting in support of activity (g): (3 trips x $6,000) = $18,000; Performing technical cooperation missions in support of activity (d): (3 missions x $4,000 = $12,000) Contractual Services For translation and editing of the comparative studies and other documents produced throughout the project in support of activities (a), (f) and (g): $20,400 Operating expenses In support of all activities: To cover reporting costs that include the cost of printing and distribution of the comparative study $15,000, other expenses related to communications, software and electronic programmes, and other miscellaneous services to support development of the electronic network and updating of the on-line database $9,550 Study Tours Horizontal technical cooperation in support of activity (d): ($3,500 per participant x 10 participants) = $35,000 Seminars and Workshops Three national workshops in support of activity (e): ($1,000 per participant x 15 participants x 3 workshops) = $45,000; and three regional workshops in support of activity (f): ($2,550 per participants x 17 participants x 3 workshops) = $130,050 |  | 57 000 241 000 30 000 78 000 20 400 24 600 35 000 175 000 |

| AF. Strengthening the capacities of Latin America and Asia to develop and improve labour training systems and to protect workers against unemployment |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ECLAC |  | Duration: 2012 – 2015 |  |
| Objective: To promote the improvement of unemployment protection and national labour training systems in three Latin American and one Asian country. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 180.0 Expert Group meetings 120.0 Travel 86.0 Contractual Services 40.0 Operating expenses 4.5 Workshops 294.0 Total 754.5 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Support for ECLAC staff (Review of global experiences and other activities): (15 months x $2,000) = $30,000 Consultants In support of activity (b): Regional consultants for regional diagnostics: (4 consultants x 2 months x $5,000) = $40,000; Local consultants for local studies, includes coordination of local working groups: (7 consultants x 5 months x $4,000) = $140,000 Expert Groups In support of activity (c) and Local working groups ($6,000 for fees + $3,000 for transport + $4,000 for DSA + $2,000 for rental of premises = $15,000 per working group x 8 working groups) = $120,000 Travel of staff In support of activities (d), (e) and (f): Initial and intermediate travel to the participating countries: (12 x $2,500) = $30,000; travel to national seminars, (8 x $2,500) = $20,000; travel to international seminar, (6 x $6,000) = $36,000 Contractual Services In support of activity (g): Preparation and translation of 8 publications in English and Spanish ($5,000 x 8) = $40,000 Operating expenses In support of activity (g): Printing materials and other communication items related to the organisation of meetings ($500 x 9) = $4,500 Seminars and Workshops In support of activities (d), (e) and (f): Local workshops (($250 per participant for 72 participants for each workshop x 4 ) = $72,000; National seminars ($300 per participant for 100 participants for each seminar x 4) = $120,000; International seminar ($3,400 per participant for 30 participants) = $102,000 |  | 30 000 180 000 120 000 86 000 40 000 4 500 294 000 |

| AG. Strengthening Information and Communications Technology capacities for disaster risk reduction and development: Addressing information, knowledge and policy gaps in Asia |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: To promote applications of information and communications technology and to enhance regional cooperation for improved disaster risk reduction and management, as well as for improved management of the associated socio-economic risks, for inclusive and sustainable development in Asia and the Pacific. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 16.0 Consultants 70.0 Expert Group meetings 85.0 Travel 60.0 Contractual Services 100.0 Workshops 269.6 Total 600.6 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Project assistance for implementation, coordination and evaluation in support of activities (a) to (e): (8 work-months x $2,000 per month) = $16,000 Consultants Regional expert services to help conduct the gap analysis, to further develop training materials, and assist government institutions on collecting information on ICT core indicators in support of activities (a) to (e): Policy study and training materials (2 consultants x 5 work months x $4,000 per month) = $40,000 and $20,000 for consultant(s) travel; Assistance on ICT indicators (1 consultant x 2.5 work months x $4,000 per month) = $10,000 Expert Groups Two regional expert meetings in support of activity (c): (10 experts from the region x $4,250 per expert per meeting x 2 meetings) = $85,000 Travel of staff Staff members of ESCAP and Asia and Pacific Training Centre for Information and Communication Technology to provide substantive services for the organization of expert meetings and training workshops in support of activities (c) and (d): ($4,000 per person x 15 individual missions) = $60,000 Contractual Services Contracts to local institutions to help organize local training on ICT core indicator methodologies, collect and process data in support of activity (b). This will cover five country studies and five national workshops x 20 participants per workshop ($500 per participant x 200 participants) Seminars and Workshops Two training workshops in support of activity (e): ($4,000 per participant x 22 participants x 2 workshops) = $176,000 and 1 regional seminar in support of activity (e): ($4,000 per participant x 22 participants) = $88,000; Reproduction of training materials of $5,600 |  | 16 000 70 000 85 000 60 000 100 000 269 600 |

| AH. Strengthening capacities in countries with special needs on designing and implementing economic and social development policies to accelerate progress towards achieving the Millennium Development Goals |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCAP, in collaboration with ECE, UNDP, other UN agencies and Asian Development Bank (ADB) |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen national capacities in countries, including those with special needs, to develop and implement economic and social policies and programmes to accelerate progress towards achieving the MDGs. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 27.0 Consultants 106.0 Expert Group meetings 21.0 Travel 58.0 Contractual Services 38.0 Operating expenses 17.5 Workshops 376.0 Total 643.5 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform the tasks in support of all activities of the project Consultants Regional / national consultants to conduct policy-oriented research in support of activities (a), (c) and (d) ($96,000); including research in the following areas: Assessment of MDG achievement by the countries with special needs focusing on the identification of development gaps and tailored-policy options for accelerating their progress towards achieving the MDGs ($13,400); Analytical research on economic and social development policy options for accelerating the progress of countries with special needs towards achieving the MDGs ($11,000); Case studies on policies towards reducing rural poverty in countries with special needs through the development of rural transport logistics and supply chains, covering specific agricultural products, to increase physical and economic access to markets and employment opportunities ($13,200); Social protection measures for promoting inclusive development and reducing poverty in the countries with special needs (using a participatory approach, involving key stakeholders in the research) ($32,000); Improving service delivery and strengthening local government institutions to accelerate progress towards achieving the MDGs ($8,800); The role of private sector in providing sustainable solutions for water and sanitation in countries with special needs ($8,800); Facilitating 2 subregional study visit-cum-training workshops For the policymakers and other stakeholders ($8,800) One regional consultant to undertake an evaluation of the project, in support of activity (e) ($10,000) Expert Groups One expert group meeting to build capacity of policymakers and experts to formulating economic and social development policies tailored to accelerate progress towards achieving the MDGs in countries with special needs in support of activity (c) (15 experts x $1,400 = $21,000) Travel of staff Travel of staff to provide advisory services upon request on designing and implementing economic and social development policies to accelerate progress towards achieving the MDGs in support of activity (b) ($17,000); Travel of ESCAP staff to organize, coordinate, promote, network and service seminars and workshops in support of activity (c) ($41,000), including: Subregional advocacy workshops for countries with special needs with focus on improving service delivery and strengthening local government institutions to accelerate progress towards achieving the MDGs; Subregional workshops to build capacity of policymakers and other key stakeholders in countries with special on designing and implementing policies towards reducing rural poverty through the development of rural transport logistics and supply chains to increase physical and economic access to markets and employment opportunities, as well as to social services. Contractual Services Publication of assessment of MDG achievement by the countries with special needs and analytical research studies/ reports/ policy briefs on economic and social development policy options for accelerating the progress of countries with special needs towards achieving the MDGs in support of activity (a) ($19,000 x 2 = $38,000) Operating Expenses In support of all activities: Communications and supplies Seminars and Workshops One regional meeting for policymakers, development researchers and practitioners, as well as those involved in the production of MDG data, in support of activity (a): (15 participants x $1,800 per participant = $27,000); One expert group meeting to build capacity of policymakers and experts to formulating economic and social development policies tailored to accelerate progress towards achieving the MDGs in countries with special needs. in support of activity (c): (15 experts x $1,527 = $22,905); Four subregional advocacy workshops for countries with special needs with focus on improving service delivery and strengthening local government institutions to accelerate progress towards achieving the MDGs. in support of activity (c): (4 x $17,400 per workshop = $69,600); Four subregional workshops to build capacity of policymakers and other key stakeholders in countries with special on designing and implementing policies towards reducing rural poverty through the development of rural transport logistics and supply chains to increase physical and economic access to markets and employment opportunities, as well as to social services in support of activity (c): (4 x $17,325 per workshop = $69,300); One regional workshop to build capacity of policymakers and other key stakeholders in countries with special on designing and implementing social protection measures for promoting inclusive development and reducing poverty to accelerate the progress towards the MDGs in support of activity (c): (1 x 15 participants x $1,765 per participant = $26,475); Public-Private Partnership roundtable to explore the role of private sector in providing sustainable solutions for water and sanitation in countries with special needs in support of activity (d): (1 x 6 participants x $1,450 per participant = $8,700); Side Events during regional and global events to highlight the issues and concerns of countries with special needs in support of activity (d): (2 side events x $21,250 per event = $42,500); Sub-regional study visit-cum-training workshops for the policymakers and other stakeholders from countries to other developing countries in support of activity (d): (2 study-cum-training workshops x $34,240 each = $68,480); Meetings of the UN Special Programme for the Economies of Central Asia Network on Trade Cooperation in support of activity (b): (2 meetings x $20,520 each = $41,040) |  | 27 000 106 000 21 000 58 000 38 000 17 500 376 000 |

| AI. Interregional cooperation to strengthen national capacities to measure progress in achieving gender equality and women’s empowerment |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCAP, in collaboration with ECE, ESCWA, and DESA |  | Duration: 2012 – 2015 |  |
| Objective: To improve the capacity of relevant national institutions in selected countries with special needs and least developed statistical systems to use data and statistics to monitor, measure and analyse progress in achieving gender equality and women’s empowerment |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 9.0 Consultants 91.0 Expert Group meetings 48.0 Travel 55.0 Contractual Services 259.0 Operating expenses 10.0 Workshops 214.4 Total 686.4 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistants (national staff), one each for three regional commissions, to assist in organizing workshops and expert group meetings, preparing LOAs, facilitating teleconferences and other project-related administrative tasks (3 assistants x 2 work months x $1,500 per month) = $9,000 Consultants National/regional consultants ($51,000): to conduct project studies, prepare training materials and other project outputs, and conduct technical assistance missions (South-South cooperation modality in support of activities (b), (c), (g), (h) and (j)) (6 consultants x 1 work month x $6,000 = $36,000) + 6 x $2,500 for travel = $15,000); International consultants ($40,000): to prepare technical notes and proposals in support of activities (a), (d), (f) and (i) (2 consultants x 1 work month x $10,000 + $2,500 for travel = $25,000) and one international consultant for project evaluation (1 consultant x $15,000 = $15,000) Expert Groups For travel of panellists and experts to regional and inter-regional expert group meetings and meetings of the technical advisory group, in relation to activities (a), (b),(d), (f) and (i) (6 experts x $8,000) = $48,000 Travel of staff Travel of staff of main implementing partners to 3 inter-regional workshops and meetings, 6 regional-level workshops, 12 national workshops and provision of technical advisory services (3 missions), in relation to activities (a) to (j) (22 persons x $2,500) = $55,000 Contractual Services Grants to project partner countries in support of activities (c ), (e), (g), (h) and (j) (4 countries x $34,750 = $139,000) + (4 countries x $30,000 = $120,000) Operating Expenses Communications and printing expenses: ESCAP 50 per cent, ESCWA 25 per cent, ECE 25 per cent in support of activities (a) through (j) Seminars and Workshops In support of activities (b), (d) and (g): Regional consultation-cum-workshop to validate core set of gender statistics: Travel and DSA of participants (38 participants x $2,000 = $76,000); Interregional workshop to take stock of good practices (8 participants x $1,750 = $14,000) + (8 participants x $2,000 = $16,000) = $30,000; Inter-regional expert group meeting to recommend mechanisms for establishing communities of knowledge (10 participants x $2,000 = $20,000); Regional-level expert group meetings of national statistical training institutes to develop a training curriculum (25 participants x $2,336 = $58,400); Interregional project closure workshop (8 participants x $1,750 = $14,000) + (8 participants x $2,000 = $16,000) = $30,000 |  | 9 000 91 000 48 000 55 000 259 000 10 000 214 400 |

| AJ. Deepening Regional Connectivity: Strengthening capacities of Asian developing countries to increase intra-regional trade by implementing paperless trade and transport facilitation systems |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCAP jointly with ECE, and in collaboration with UNCTAD |  | Duration: 2012 – 2015 |  |
| Objective: To build national governments’ capacity to implement paperless systems for cross-border trade and transport and support implementation of national and regional single windows. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 45.0 Consultants 150.0 Expert Group meetings 70.0 Travel 104.0 Contractual Services 60.0 Operating expenses 25.0 Workshops 400.0 Total 854.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance in support of activities (a) to (e) (18 months x $2,500 per month) = $45,000 Consultants Regional consultants for preparing technical and policy briefs (10 briefs x $2,000) = $20,000 and paperless system assessment studies (8 work months x $6,000) = $48,000; and (4 international travels at $3,000) = $12,000 under activity (a); delivery of specialized technical support and advisory services (5 work months x $6,000) = $30,000 and (8 international travels at $3,000) = $24,000 under activity (e); and external project evaluation of $16,000 Expert Groups Organize at least 3 Advisory Group Meetings under activity (c): ($2,500-$3,000 of 8-9 international travels of experts x 3) Travel of staff Staff travel to support activities (a) to (e): in particular organization and coordination of forums ($3,000 x 6 persons travel x 2 forums) = $36,000, four subregional workshops ($3,000 x 3 persons travel x 4) = $36,000, three advisory group meetings ($3,000 x 4-6 staff ) = $16,000, and advisory services and other project activities as needed ($3,000 x 4-6 staff) = $16,000 Contractual Services Development of Guides and training materials, including translation and publication/printing under activity (d): (3 published guides and associated training materials in 2 official languages x $20,000) = $60,000. Note: guide development may be done using Consultants if this is found to be more cost effective Operating Expenses Communication in support of activities (a) to (e): ($5,000 per year x 3) = $15,000; Supplies in support of activities (a) to (e): ($10,000 for 3 years) = $10,000 Seminars and Workshops Two regional forums and back-to-back workshops under activity (a) and (d): ($3,000 for 40 participants x 2 workshops) = $240,000; Four subregional workshops under activity (d): ($2,000 for 20 participants x 4 workshops) = $160,000 |  | 45 000 150 000 70 000 104 000 60 000 25 000 400 000 |

| AK. Institutional and capacity building for Arab Parliaments and other stakeholders for the implementation of Security Council resolution 1325 (2000) on Women, Peace and Security |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCWA in collaboration with ECA |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen the capacity of Arab parliaments to implement Security Council resolution 1325 (2000) on Women, Peace and Security |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 15.0 Consultants 87.9 Expert Group meetings 52.2 Travel 70.4 Contractual Services 40.2 Operating expenses 0.5 Workshops 243.8 Total 510.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform the task of administrative assistant, in support the implementation of activities (b,) (d) and (f): (6 work months x $2,500) = $15,000 Consultants National consultant ($73,900): two national consultants (from the Arab region) for undertaking the regional study, preparing the training manuals and the virtual evaluation workshop in support of activities (b), (c), (d), (e) and (g): (2 work months x $6,000 per month x 2 consultants) = $24,000 + (1 work month x $3,000 per month x 1 consultant) = $3,000 + ($2,875 for travel x 3 missions x 1consultant) = $8,625; four national consultants (from the Arab region) for undertaking the four training of trainers in support of activity (f): (3 work days x $500 per day x 4 workshops x 2 consultants) = $12,000 + ($3,116 for travel x 2 workshops x 2 consultants) = $12,464 + ($3,156 for travel x 2 workshops x (2 consultants) = $12,624; one Facilitator, in support of activity (d): ($1,200) x one facilitator) = $1,200; International Consultant ($14,000): External Evaluation Consultant for the mandatory final evaluation. (2 work months x $7,000 per month) = $14,000 Expert Groups Two expert group meetings in Lebanon in support of activities (b) and (d): ($2,175 per participant x 12 participants x 2 ) = $52,200 Travel of staff ESCWA Staff: Two missions by ESCWA staff to participate as resource person in support of activity F ($ 3,356 per person x 2 persons x 2 missions to Rabat) = $13,424; Regional Commissions’ staff / other UN staff: To participate as resource persons in expert meeting and regional seminar, in support of activities (b), (d) and (f): ($ 3,475 per person x 2 persons x 2 missions to Beirut) = $13,900; ($3,716 per person x 4 persons x 2 missions to Beirut) = $29,728; ($3,356 per person x 2 persons x 2 missions to Rabat) = $13,424 Contractual Services Interpretation (services provided by a company or institutional contracts): Interpretation services in support of activities (b) and (d): ($350 per person x 2 persons x 2 days x 2 activities) = $2,800; Interpretation services in support of activity (f): ($350 per person x 2 persons x 3 days x 4 workshops) = $8,400; Translation (services provided by a company or institutional contracts) Translation of documents into English in support of activities (c) and (e): ($3,500 per document x 2 documents) = $7,000; Website/web portal/ knowledge platform support (services provided by a company or institutional contracts); Website support to facilitate activities H = $9,000; Printing Cost (services provided by a company or institutional contracts); Printing of publication in support of activities (c) and (e): ($5,000 per document x 2 documents) = $10,000; Graphic Design Cost (services provided by a company or institutional contracts); Graphic design services in support of activities (c) and (e): ($1,500 per document x 2 documents) = $3,000 Operating Expenses Communications, in support of activity (a): $500 Seminars and Workshops Two workshops in Lebanon in support of activity (f): ($2,416 per participant x 24 participants x 2 workshops) = $115,968; 2 workshops in Rabat in support of activity (f): ($2,556 per participant x 24 participants x 2 workshops) = $122,688; Meeting related expenditures: 2 Expert Group Meetings in Lebanon in support of activities (b) and (d) = $880; 4 workshops in support of activity (f) = $4,320 |  | 15 000 87 900 52 200 70 400 40 200 500 243 800 |

| AL. Academy of ICT Essentials for Government Leaders in the ESCWA Region (AIGLE) |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCWA in collaboration with ESCAP |  | Duration: 2012 – 2015 |  |
| Objective: To enhance the application of ICT in improving the socio-economic development of the ESCWA region |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 45.0 Consultants 116.0 Travel 46.0 Contractual Services 65.0 Operating expenses 8.0 Equipment and Supplies 5.0 Workshops 224.0 Total 509.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform the task of Research Assistant to support the implementation of all activities, (by undertaking research, following up on consultancies, drafting substantive input for meetings, workshops and trainings, etc). (15 work months x $3,000 per month) = $45,000 Consultants National/Regional consultants ($105,000): 1 regional consultant to assist in the review of existing ICTD training programmes, including a needs assessment survey involving at least 8 ESCWA countries, the analysis of the modules provided by the Asia and Pacific Training Centre for Communication and Information Technology, and the identification of new relevant topics, in support of activity (a): (2 work months x $8,000 per month x 1 national/regional consultant)= $16,000; 3 National / regional consultants to assist in localizing the selected modules and / or developing the new relevant topics to be added and their related modules in support of activity (a) and delivering the related training during the activity (d). (3 work months) x $7,000 per month x 3 national/regional consultants) = $63,000; 1 National / regional consultant to assist in designing, editing and publishing the entire package of the academy in support of activity (b). (2 work months x $6,000 per month x 1 national/regional consultant)= $12,000; 1 National / regional consultant to assist in conducting the Academy Impact Assessment and to participate and present findings during the related regional workshop, in support of activity (f): (2 work months) x $7,000 per month x 1 national/regional consultant)= $14,000; External Evaluation Consultant ($11,000): 1 External Evaluation Consultant for the mandatory final evaluation: (1 work month) x $7,000 per month) = $7,000 + ($2,000 for travel x 2 trips) = $4,000 Travel of staff ESCWA Staff: Six missions by ESCWA staff for the purpose of providing technical assistance during the different national training workshops implemented in the various ESCWA member countries, in support of activity (e): 2 staff members x $2,500 per mission x 6 missions = $30,000; Regional Commissions’ staff / other UN staff: 1 expert from APCICT / ESCWA to participate as resource person in two workshops: Training of Trainer workshop and Academy Impact Assessment regional workshop, in support of activities (d) and (f). ($3,334 per person x 1 person x 3 trips) = $10,000; 1 expert from ECA to participate in one Training of Trainers Workshops and in the Academy Impact Assessment regional workshop, in support of activities (d) and (f). ($3,000 per person x 1 person x 2 trips) = $6,000 Contractual Services Developing the Academy Online Training Platform (services provided by a company or institutional contracts) Website support to facilitate activities (c) = $50,000; Publishing Academy Package: (Training Material) In support of activity (b): (300 copies x $50 per copy) = $15,000 Operating Expenses Communications: in support of all activities: $2,000; Supplies: in support of activities (d) and (f): $2,000; Low-value printing: in support of activities (a), (c), (d) and (f): $4,000 Equipment and supplies Office equipment: 1 server to host the Academy Online Training Platform, in support of activity (c): $5,000 Seminars and Workshops Three regional Training of Trainers workshops, 4 days each, in support of activity (d): ($2,000 per participant x 28 participants x 3 workshops) = $168,000; 1 regional evaluation workshop, in support of (f): ($2,000 per participant x 28 participants) = $56,000 |  | 45 000 116 000 46 000 65 000 8 000 5 000 224 000 |

| AM. Developing the Capacities of the Arab Countries for Climate Change Adaptation by Applying Integrated Water Resource Management Tools |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCWA jointly with UNEP Regional Office for West Asia |  | Duration: 2012 – 2015 |  |
| Objective: To develop the capacity of Arab Governments to adapt to climate change by applying integrated water resource management tools in the key sectors that will be affected by climate change impacts on freshwater resources. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 18.0 Consultants 177.0 Expert Meetings 23.8 Travel 24.7 Contractual Services 31.5 Operating expenses 0.8 Workshops 241.2 Total 517.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance Temporary assistance to perform the tasks of administrative and technical support for limited periods during project implementation: (6 work months x $3,000 per month) = $18,000 Consultants Expert consultants (regional or international) for the preparation of the five training modules and their contribution to the five training workshops, in support of activity (b), (c), and (d): (3.9 work months x $8,000 per month x 5 training modules) = $156,000; Travel of experts to the training workshops with an average duration of 4 days, in support of activity (c): ($2,000 per participant x 5 participants) = $10,000; External Evaluation Consultant: = $11,000 Expert Meetings Travel of expert consultants to expert meeting to present draft training modules with an average duration of 2 days, in support of activity (b): ($1,400 per participant x 5 participants) = $7,000; Travel of non-UN partners and participants to expert meeting (Beirut) to review and comment on draft training modules with an average duration of 2 days, in support of activity (b): ($1,400 per participant x 12 participants) = $16,800 Travel of staff ESCWA Staff Travel: Travel of staff to training workshops with an average duration of 4 days, in support of activity (c): ($1,500 per participant x 3 staff members x 2 workshops in Amman) = $9,000; Travel of staff in relation to the presentation of the Integrated Water Resources Management (IWRM) training modules and manual with an average duration of 4 days, in support of activity (e): ($2,100 average mission cost x 1 person x 1 mission) = $2,100; UNEP/ROWA, ECA and WHO/CEHA Staff Travel: Travel of partners from UN agencies to the inception meeting (Beirut) to set the terms of reference for training modules, with an average duration of 2 days, in support of activity (a): ($1,350 per participant x 3 UN participants) = $4,050; Travel of UN partners to expert meeting (Beirut) to review and comment on draft training modules with an average duration of 2 days, in support of activity (b): ($1,350 per participant x 3 UN participants) = $4,050; Travel of UN partners to training workshops (Beirut or Amman) with an average duration of 4 days, in support of activity (c): ($1,850 per participant x 3 UN participants) = $5,550 Contractual Services Interpretation: A contract to be given to an individual or institution for interpretation services in support of activity (c): ($368 per person x 2 persons x 3 days x 5 workshops) = $11,040; Translation: A contract to be given to an individual or institution for translation (Arabic-English) of the five training modules and final IWRM training manual, in support of activity (c) and (e): ($40 per page for translation x 40 page/training module x 5 modules) = $8,000; ($20 per page for adjustment x 200 page IWRM training manual) = $4,000; Design and Printing: A contract to be given to an individual or institution for the design of the training modules and training manual, in support of activity (c) and (e): ($1,000 per design x 2 units) = $2,000; A contract to be given to an individual or institution for printing of training modules for workshops and manual, in support of activity (c) and (e): ($300 per 40 page training module x 5 modules) = $1,500; ($5,000 per 200 pages training manual x 1 manual) = $5,000 Operating Expenses Operating expenses for postage, communications, low-value printing services, etc.: $800 Seminars and Workshops Working Group: Travel of non-UN partners to inception meeting (Beirut) to set the terms of reference for training modules with an average duration of 2 days, in support of activity (a): ($800 per participant x 2 partners) = $1,600; Workshops: Travel of participants to five training workshops (Beirut or Amman). Each workshop is to be attended by 24 participants from 22 Arab member state,1 participant from each Arab member states (22), plus 2 participants from Arab Integrated Water Resources Management Network (2), with an average duration of 4 days, in support of activity (c): ($1,750 per participant x 24 participants x 5 training workshops) = $210,000; Travel of non-UN partners to training workshops (Beirut or Amman) with average duration of 4 days, in support of activity (c): ($1,300 per participant x 2 partners) = $2,600; Rental of workshop venue and related equipments: ($10,000 per workshop x 2 workshops in Amman) = $20,000; Organization of meetings and workshops: Organizational expenses for the inception meeting, expert meeting and workshops, in support of activity (a), (b), and (c): ($1,000 per meeting x 7 meetings) = $7,000 |  | 18 000 177 000 23 800 24 700 31 500 800 241 200 |

| AN. Strengthening capacities to utilise workers’ remittances in financing for development |  |  |  |
| --- | --- | --- | --- |
| Implementing entities: ESCWA in cooperation with ECA and DESA |  | Duration: 2012 – 2015 |  |
| Objective: To strengthen capacities of government officials to formulate and adopt strategies, policies and programmes to enhance the impact of workers’ remittances in financing for development in nine labour-exporting Arab states. |  |  |  |
| Summary budget (Thousands of United States dollars) GTA 30.0 Consultants 160.0 Travel 75.0 Contractual Services 10.0 Operating expenses 9.0 Workshops 180.0 Total 464.0 | ## Detailed budget (US dollars) |  |  |
|  | General Temporary Assistance A provision of $30,000 is required to assist in holding workshops, seminars and establishing platform, in support the implementation of activities (b), (c), (d) and (e): (12 work months x $2,500 per month) = $30,000 Consultants International consultant ($65,000): 13 international consultants to prepare different technical material on successful experiences and good practices in utilising remittances for development finance, run nine workshops and 3 subregional seminars, in support of activities (b), (c) and (d): (0.5 work months x $5,000 per month x 13 consultants = $$32,500) + ($2,500 for travel x 13 consultants = $32,500); Regional consultant ($75,000): 6 regional consultants (from Egypt, Lebanon, Morocco, Tunisia, Sudan and Yemen) to carry out and present national studies on formulating practical policies to enhance the impact of remittances in financing for development and, in support of activities (a), (b), and (c): (2.5 work months x $5,000 per month x 6 consultants) = $75,000 External Evaluation Consultant ($20,000): External Evaluation Consultant for the mandatory final evaluation: (2 work months x $5,000 per month) = $10,000 + ($2,500 for travel x 4 trips) = $10,000 Travel of staff ESCWA Staff: 10 missions by ESCWA staff for the purpose of organizing 2 subregional seminars, 5 national workshops, and provide advisory services to member states, in support of activities (b), (c), (d) and (e): ($2,500 per person x 2 persons x 10 missions)] = $50,000; Regional Commissions’ staff / other UN staff: To organize 1 subregional seminar, 3 national workshops, provide advisory services to member states and participate as resource persons in subregional seminars and national workshops, in support of activities (b), (c), and (e): ($2,500 per person x 2 x 5 trips) = $25,000 Contractual Services Translation (services provided by a company or institutional contracts): Simultaneous translation from French to Arabic and English and translation of documents into English and Arabic in support of activities (b): ($300 per document x 10 number of documents) = $3,000 + ($700 per day x 2 persons x 5 days) = $7,000 Operating Expenses Communications: In support of activities (a), (b) and (c) = $5,000; Low-value printing: In support of activities (a), (b), (c) and (d) = $4,000 Seminars and Workshops Three seminars in Syria, Tunisia, and Egypt in support of (b) and (c). ($2,500 per participant) x 24 participants x 3 seminars)] = $180,000 |  | 30 000 160 000 75 000 10 000 9 000 180 000 |

*	*	Not for distribution

UNCTAD will sponsor 10 participants per seminar. These activities will also be open to concerned participants not sponsored through this project.