Implementation Plan of Recommendations

| Project Title and Reference No. Coherent Integration of the Environmental Dimension of the Sustainable Development Goals in Regional and National Policy Frameworks in Africa PIMS ID Number - 02086 |  |
| --- | --- |
| Contact Person (TM/PM): Robert Wabunoha, Regional Coordinator, Environmental Governance |  |

|  | PLANS |  |  |  |
| --- | --- | --- | --- | --- |
| RECOMMENDATIONS | ACCEPTED (YES/NO/PARTIALLY) | ACTIONS THAT WERE TAKEN | EXPECTED COMPLETION DATE | REPONSIBLE OFFICER/ UNIT/ DIVISION/ AGENCY |
| 1. Write a comprehensive end of project report that captures and documents the many and useful outputs and results produced by the project. | Yes | The UNDA-specific final report was already submitted to the UNDA focal point, which documented the results of the UNDA project (2124G). | Completed in March 2024 | Robert Wabunoha/UNEP UNEP Project Management Committee |
| 2. Undertake detailed review of sub-projects, where deemed appropriate. | Partially | This has been acknowledged as a forward-looking lesson for future design and programming, rather than a requirement for retrospective action on concluded projects. The design of future umbrella projects will include provisions for detailed reviews of sub-projects funded by UNDA. Besides, lessons learned from the UNDA project (2124G) have been incorporated into the following UNEP projects. Lessons learned have also been shared with the UNCTs across Africa. - The Waste Methane Project in Côte d’Ivoire, now being implemented across Africa, applies UNDA lessons on embedding interventions into national academic curricula to enhance policy uptake. - NAPs implementation support in various countries has been enriched by UNDA lessons on using cross-sectoral coherence to strengthen resilience planning and value-added adaptation pathways. - The REDD+ project under development is drawing from lessons on leveraging community structures to drive local capacity and uptake of climate action. - The UNEP Freshwater Strategy, currently being led by the Ecosystems Division, incorporates lessons from UNDA on improving policy coherence and addressing implementation silos. - EBA-focused work in Benin and The Gambia builds on tested UNDA approaches, such as using communal structures, clean energy linkages, and national standards to scale uptake. | This will be undertaken when and if a new UNDA-funded project materializes. Meanwhile, as described in the left-hand column, a few new UNEP projects have already incorporated lessons learned from the UNDA project (2124G). | Robert Wabunoha/UNEP |
| 3. Monitor human rights, gender, social and environmental safeguard in the follow-up project: | Partially | Future projects will be designed to set a reporting arrangement on human rights, gender, social and environmental safeguards. For example, the UN REDD+ project has already incorporated monitoring of human rights, gender, and social and environmental safeguards in its project design. | This will be taken in the design and implementation of future projects. | Robert Wabunoha/UNEP |